## Procurement Tracker
Material Procurement Tracker
Track construction material procurement — quantities, costs, suppliers, delivery status, and PO details
S.No. | Date | Material Name | Category | Unit | Qty Required | Qty Ordered | Qty Received | Unit Price (AED) | Total Cost (AED) | Supplier Name | PO Number | Expected Delivery | Status | Remarks
1 | 2026-01-01 | Portland Cement OPC 43 | Cement | Bag | 500 | 500 | 480 | 32.5 | 16250 | Gulf Cement LLC | PO-2026-0101 | 2026-01-05 | Delivered
2 | 2026-01-02 | TMT Steel Bars 12mm | Steel | MT | 10 | 10 | 10 | 3800 | 38000 | Steel Arabia Co. | PO-2026-0102 | 2026-01-04 | Delivered
3 | 2026-01-03 | River Sand | Aggregates | m³ | 80 | 80 | 75 | 120 | 9600 | Al Noor Aggregates | PO-2026-0103 | 2026-01-06 | Partial
4 | 2026-01-04 | Coarse Aggregate 20mm | Aggregates | m³ | 60 | 60 | 60 | 135 | 8100 | Al Noor Aggregates | PO-2026-0104 | 2026-01-06 | Delivered
5 | 2026-01-05 | Red Clay Bricks | Masonry | Nos | 15000 | 15000 | 14000 | 3.2 | 48000 | Brick Masters LLC | PO-2026-0105 | 2026-01-08 | Partial
6 | 2026-01-06 | Waterproofing Compound | Chemical | Ltr | 200 | 200 | 200 | 85 | 17000 | Chem Solutions UAE | PO-2026-0106 | 2026-01-07 | Delivered
7 | 2026-01-07 | PVC Pipes 4 inch | Plumbing | Mtr | 300 | 300 | 300 | 45 | 13500 | PVC World Dubai | PO-2026-0107 | 2026-01-09 | Delivered
8 | 2026-01-08 | GI Wire Mesh | Steel | Roll | 50 | 50 | 0 | 180 | 9000 | Steel Net Co. | PO-2026-0108 | 2026-01-15 | Pending
9 | 2026-01-09 | Ceramic Floor Tiles | Finishing | Box | 400 | 400 | 0 | 220 | 88000 | Tile Gallery LLC | PO-2026-0109 | 2026-01-20 | Pending
10 | 2026-01-10 | White Cement | Cement | Bag | 100 | 100 | 100 | 48 | 4800 | Gulf Cement LLC | PO-2026-0110 | 2026-01-10 | Delivered
11 | 2026-01-11 | Electrical Conduit Pipe | Electrical | Mtr | 500 | 500 | 400 | 28 | 14000 | Electro Pipes LLC | PO-2026-0111 | 2026-01-12 | Partial
12 | 2026-01-12 | CPVC Pipes 1 inch | Plumbing | Mtr | 200 | 200 | 200 | 38 | 7600 | CPVC Solutions | PO-2026-0112 | 2026-01-11 | Delivered
13 | 2026-01-13 | Structural Steel I-Beam | Steel | MT | 5 | 5 | 5 | 4200 | 21000 | Steel Arabia Co. | PO-2026-0113 | 2026-01-08 | Delivered
14 | 2026-01-14 | Paint Primer | Finishing | Ltr | 150 | 150 | 0 | 65 | 9750 | ColourMax UAE | PO-2026-0114 | 2026-01-22 | Pending
15 | 2026-01-15 | Plywood 18mm | Wood | Sheet | 80 | 80 | 80 | 420 | 33600 | Wood & More LLC | PO-2026-0115 | 2026-01-09 | Delivered
16 | 2026-01-16 | Door Frames Teak | Wood | Nos | 20 | 20 | 15 | 1800 | 36000 | Teak Craft LLC | PO-2026-0116 | 2026-01-14 | Partial
17 | 2026-01-17 | Glass 6mm Toughened | Glazing | Sft | 500 | 500 | 0 | 95 | 47500 | Glass Tech UAE | PO-2026-0117 | 2026-01-25 | Pending
18 | 2026-01-18 | Bitumen Waterproofing | Chemical | Kg | 300 | 300 | 300 | 72 | 21600 | Bitumen Gulf LLC | PO-2026-0118 | 2026-01-10 | Delivered
19 | 2026-01-19 | Aluminium Shuttering | Formwork | Sft | 1000 | 1000 | 1000 | 55 | 55000 | Form Work UAE | PO-2026-0119 | 2026-01-07 | Delivered
20 | 2026-01-20 | Binding Wire | Steel | Kg | 100 | 100 | 100 | 85 | 8500 | Steel Arabia Co. | PO-2026-0120 | 2026-01-05 | Delivered

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit