## Subcontractor Payments
Subcontractor Payment Tracker
Track all subcontractor contracts, invoices, advance payments, retention, net payable amounts, and payment status
S.No. | Subcontractor | Trade | Contract Value (AED) | Advance Paid | Invoice No. | Invoice Date | Invoice Amount | Retention % | Retention Held | Net Payable | Payment Date | Payment Mode | Balance Due | Status
1 | Al Baraka Contractors | Civil | 450000 | 180000 | INV-SC-001 | 2026-01-05 | 85000 | 10% | 8500 | 76500 | 2026-01-20 | Bank Transfer | 108500 | Partial
2 | Gulf Build LLC | Structural | 970000 | 300000 | INV-SC-002 | 2026-01-06 | 120000 | 10% | 12000 | 108000 | 2026-01-21 | Cheque | 562000 | Partial
3 | NK Civil Works | Masonry | 195000 | 80000 | INV-SC-003 | 2026-01-07 | 45000 | 10% | 4500 | 40500 | 2026-01-22 | Bank Transfer | 74500 | Partial
4 | PowerTech MEP | Electrical | 150000 | 60000 | INV-SC-004 | 2026-01-08 | 35000 | 10% | 3500 | 31500 | 2026-01-23 | Bank Transfer | 58500 | Partial
5 | AquaFlow MEP | Plumbing | 130000 | 50000 | INV-SC-005 | 2026-01-09 | 30000 | 10% | 3000 | 27000 | 2026-01-24 | Cheque | 53000 | Partial
6 | WaterPro UAE | Waterproofing | 85000 | 0 | INV-SC-006 | 2026-01-10 | 20000 | 10% | 2000 | 18000 |  | Pending | 67000 | Unpaid
7 | AlumPro UAE | Aluminium | 180000 | 70000 | INV-SC-007 | 2026-01-11 | 50000 | 10% | 5000 | 45000 | 2026-01-26 | Bank Transfer | 65000 | Partial
8 | Tile Masters LLC | Tiling | 165000 | 55000 | INV-SC-008 | 2026-01-12 | 55000 | 10% | 5500 | 49500 | 2026-01-27 | Cheque | 54500 | Partial
9 | Royal Sanitary UAE | Sanitary | 95000 | 40000 | INV-SC-009 | 2026-01-13 | 40000 | 10% | 4000 | 36000 | 2026-01-28 | Bank Transfer | 19000 | Partial
10 | ColourMax UAE | Painting | 90000 | 0 | INV-SC-010 | 2026-01-14 | 0 | 10% | 0 | 0 |  | Not Invoiced | 90000 | Pending
11 | Cool Air Systems | HVAC | 200000 | 80000 | INV-SC-011 | 2026-01-15 | 0 | 10% | 0 | 0 |  | Not Started | 120000 | Pending
12 | SafeGuard Tech | Security | 45000 | 20000 | INV-SC-012 | 2026-01-05 | 25000 | 10% | 2500 | 22500 | 2026-01-15 | Bank Transfer | 0 | Paid
13 | Kitchen World UAE | Kitchen | 120000 | 50000 | INV-SC-013 | 2026-01-16 | 0 | 10% | 0 | 0 |  | Not Started | 70000 | Pending
14 | Glass Tech UAE | Glazing | 47500 | 0 | INV-SC-014 | 2026-01-17 | 0 | 10% | 0 | 0 |  | Not Invoiced | 47500 | Pending
15 | Green Thumb LLC | Landscaping | 65000 | 0 |  |  | 0 | 10% | 0 | 0 |  | Not Started | 65000 | Not Started
16 | Form Work UAE | Formwork | 55000 | 20000 | INV-SC-015 | 2026-01-18 | 35000 | 10% | 3500 | 31500 | 2026-01-25 | Cheque | 0 | Paid
17 | Bitumen Gulf LLC | Waterproofing | 21600 | 10000 | INV-SC-016 | 2026-01-05 | 11600 | 10% | 1160 | 10440 | 2026-01-12 | Cash | 0 | Paid
18 | PVC World Dubai | Plumbing | 13500 | 5000 | INV-SC-017 | 2026-01-05 | 8500 | 10% | 850 | 7650 | 2026-01-12 | Cash | 0 | Paid
19 | Smart Tech Solutions | Automation | 3500 | 0 | INV-SC-018 | 2026-01-19 | 3500 | 10% | 350 | 3150 |  | Pending | 3500 | Unpaid
20 | NK Civil Works | Plastering | 75000 | 30000 | INV-SC-019 | 2026-01-20 | 25000 | 10% | 2500 | 22500 |  | Pending | 22500 | Unpaid

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit