## Equipment Rental
Equipment Rental Cost Tracker
Track all construction equipment rentals — rates, dates, total costs, invoices, operators, and payment status
S.No. | Equipment Name | Category | Vendor | Rate (AED/day) | Start Date | End Date | Days | Total Cost | Invoice No. | Payment Status | Location | Operator | Condition | Notes
1 | Tower Crane 25-ton | Lifting | Gulf Crane Co. | 2800 | 2026-01-01 | 2026-03-31 | 90 | 252000 | RC-INV-001 | Pending | Zone A | Ahmed Operator | Good | Milestone billing
2 | Excavator CAT 320 | Earthmoving | Al Baraka Plant | 950 | 2026-01-02 | 2026-01-20 | 19 | 18050 | RC-INV-002 | Paid | Zone B | Hassan Driver | Good | Returned on schedule
3 | Concrete Mixer 500L | Concreting | Build Tech UAE | 280 | 2026-01-05 | 2026-02-28 | 55 | 15400 | RC-INV-003 | Paid | Zone A | Raj Kumar | Good
4 | Boom Lift 20m | Access | Sky Access UAE | 650 | 2026-01-08 | 2026-01-31 | 24 | 15600 | RC-INV-004 | Paid | Level 2 | Omar Driver | Good | External cladding
5 | Scaffolding 500sqm | Access | SafeScaffold LLC | 180 | 2026-01-01 | 2026-06-30 | 181 | 32580 | RC-INV-005 | Partial | Building | N/A | Good | 50% advance paid
6 | Bulldozer D6 | Earthmoving | Al Baraka Plant | 1100 | 2026-01-10 | 2026-01-25 | 16 | 17600 | RC-INV-006 | Paid | Zone C | Raj Driver | Good | Site levelling
7 | Water Pump 4-inch | Utilities | Pump World UAE | 120 | 2026-01-01 | 2026-02-28 | 59 | 7080 | RC-INV-007 | Paid | Basement | Site Team | Good | Dewatering
8 | Compactor Plate 500kg | Earthmoving | Build Tech UAE | 150 | 2026-01-05 | 2026-01-31 | 27 | 4050 | RC-INV-008 | Paid | Zone B | Site Team | Good
9 | Generator 100KVA | Power | PowerGen UAE | 800 | 2026-01-01 | 2026-03-31 | 90 | 72000 | RC-INV-009 | Partial | Site Office | Electrical Team | Good | Primary power
10 | Road Header | Drilling | Gulf Drill Co. | 2200 | 2026-01-12 | 2026-01-30 | 19 | 41800 | RC-INV-010 | Paid | Zone D | Specialist Crew | Good | Foundation drilling
11 | Transit Mixer 6m3 | Concreting | Concrete Plus UAE | 450 | 2026-01-15 | 2026-03-15 | 60 | 27000 | RC-INV-011 | Partial | Zone A | Ahmed Driver | Good | Slab pours
12 | Scissor Lift 10m | Access | Sky Access UAE | 380 | 2026-01-20 | 2026-02-28 | 40 | 15200 | RC-INV-012 | Pending | Level 3 | Site Team | Good | Fit-out work
13 | Vibratory Roller 8-ton | Earthmoving | Al Baraka Plant | 750 | 2026-01-18 | 2026-02-05 | 19 | 14250 | RC-INV-013 | Paid | External | Raj Driver | Good | Road compaction
14 | Concrete Pump Truck | Concreting | Concrete Plus UAE | 1800 | 2026-01-10 | 2026-01-15 | 6 | 10800 | RC-INV-014 | Paid | Zone A | Specialist | Good | High-rise pour
15 | Forklift 5-ton | Lifting | Gulf Crane Co. | 350 | 2026-01-01 | 2026-03-31 | 90 | 31500 | RC-INV-015 | Partial | Warehouse | Hassan Driver | Good | Material handling
16 | Welding Machine Set | Fabrication | Welding World UAE | 80 | 2026-01-05 | 2026-02-28 | 55 | 4400 | RC-INV-016 | Paid | Fabrication | Welder Team | Good
17 | Air Compressor 7-bar | Utilities | Build Tech UAE | 95 | 2026-01-01 | 2026-03-31 | 90 | 8550 | RC-INV-017 | Partial | Site-wide | Site Team | Good | Tools and equipment
18 | Dewatering Pump 6-inch | Utilities | Pump World UAE | 180 | 2026-01-08 | 2026-02-08 | 32 | 5760 | RC-INV-018 | Paid | Basement | Site Team | Good | Rainfall period
19 | Batching Plant 30m3/hr | Concreting | Concrete Plus UAE | 3500 | 2026-01-01 | 2026-03-31 | 90 | 315000 | RC-INV-019 | Partial | Site Yard | Plant Operator | Good | On-site batching
20 | Piling Rig | Foundation | Gulf Drill Co. | 4500 | 2026-01-03 | 2026-01-20 | 18 | 81000 | RC-INV-020 | Paid | Zone D | Specialist Crew | Good | Bored pile foundation

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit