## Labour Cost Estimation
Labour Cost Estimation Sheet
Estimate construction labour costs by trade — workers, daily rates, working days, overtime, allowances, and total cost per trade
S.No. | Trade / Labour Type | Skill Level | No. of Workers | Daily Rate (AED) | Working Days | Basic Labour Cost | Overtime Days | OT Rate (AED/day) | OT Cost | Allowances (AED) | Insurance (AED) | Total Labour Cost | Cost per m2 | Remarks
1 | Project Manager | Senior | 1 | 1200 | 90 | 108000 | 10 | 600 | 6000 | 5000 | 2160 | 121160 | 0 | Fixed monthly equivalent
2 | Site Engineer | Senior | 2 | 900 | 90 | 162000 | 15 | 450 | 13500 | 4000 | 3240 | 182740 | 0 | 2 engineers for full project
3 | Civil Foreman | Senior | 3 | 600 | 90 | 162000 | 20 | 300 | 18000 | 3000 | 3240 | 186240 | 0
4 | Skilled Mason | Skilled | 20 | 350 | 90 | 630000 | 10 | 175 | 35000 | 8000 | 12600 | 685600 | 12.5 | Brick and block work
5 | Concrete Worker | Skilled | 15 | 320 | 60 | 288000 | 8 | 160 | 19200 | 5000 | 5760 | 317960 | 8.2 | Slab and column pours
6 | Steel Fixer / Binder | Skilled | 12 | 340 | 60 | 244800 | 8 | 170 | 16320 | 4500 | 4896 | 270516 | 6.8 | Rebar work
7 | Carpenter (Formwork) | Skilled | 10 | 320 | 45 | 144000 | 5 | 160 | 8000 | 3500 | 2880 | 158380 | 4.5 | Formwork and shuttering
8 | Electrical Worker | Skilled | 8 | 380 | 60 | 182400 | 5 | 190 | 7600 | 3000 | 3648 | 196648 | 5.2 | First and second fix
9 | Plumber | Skilled | 6 | 360 | 60 | 129600 | 5 | 180 | 5400 | 2500 | 2592 | 140092 | 3.8 | Rough-in and fit-out
10 | Tile Setter | Skilled | 8 | 340 | 30 | 81600 | 0 | 170 | 0 | 2000 | 1632 | 85232 | 2.5 | Floor and wall tiling
11 | Painter | Semi-Skilled | 10 | 280 | 30 | 84000 | 0 | 140 | 0 | 2000 | 1680 | 87680 | 2.2 | Internal and external paint
12 | Plasterer | Skilled | 8 | 300 | 30 | 72000 | 0 | 150 | 0 | 1800 | 1440 | 75240 | 2 | Internal plaster
13 | Unskilled Labour | Unskilled | 20 | 220 | 90 | 396000 | 10 | 110 | 22000 | 5000 | 7920 | 430920 | 9.5 | General site labour
14 | Waterproofing Applicator | Skilled | 4 | 320 | 10 | 12800 | 0 | 160 | 0 | 800 | 256 | 13856 | 0.5 | Waterproofing specialist
15 | HVAC Technician | Skilled | 4 | 420 | 20 | 33600 | 0 | 210 | 0 | 1000 | 672 | 35272 | 1 | AC installation
16 | Safety Officer | Senior | 1 | 700 | 90 | 63000 | 0 | 350 | 0 | 2000 | 1260 | 66260 | 0 | Site safety full-time
17 | Surveyor | Senior | 1 | 800 | 90 | 72000 | 5 | 400 | 2000 | 2000 | 1440 | 77440 | 0 | Setting out and checks
18 | QC Inspector | Senior | 1 | 750 | 90 | 67500 | 0 | 375 | 0 | 2000 | 1350 | 70850 | 0 | Quality control
19 | Aluminium Fabricator | Skilled | 4 | 380 | 20 | 30400 | 0 | 190 | 0 | 800 | 608 | 31808 | 0.8 | Windows and doors
20 | Glazier | Skilled | 2 | 360 | 10 | 7200 | 0 | 180 | 0 | 400 | 144 | 7744 | 0.2 | Glass installation

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit