## Snag List Tracker
Snag List Tracker — Defect Management
ExcelGurukulOnline.com ¦ Construction & Engineering · Site Management
Snag ID | Location | Floor | Trade | Description of Defect | Severity | Raised By | Date Raised | Assigned To | Due Date | Status | Closed Date | Notes
SNL-001 | Master Bedroom | G | Painting | Paint peeling near window sill | Medium | Site Engr | 01-May-26 | XYZ Painters | 08-May-26 | Closed | 07-May-26 | Repainted — OK
SNL-002 | Kitchen | G | Tiles | Tile hollow sound at 3 spots | High | Client | 02-May-26 | Tile Masters | 09-May-26 | Open |  | Client to confirm access
SNL-003 | Bathroom 2 | G | Plumbing | Hot water tap leaking | High | Site Engr | 02-May-26 | AquaFit | 07-May-26 | Closed | 06-May-26 | Washer replaced
SNL-004 | Living Room | G | Electrical | Switch plate not aligned | Low | QC | 03-May-26 | PowerTech | 10-May-26 | Open
SNL-005 | Balcony | G | Civil | Drain choked — water stagnating | High | Client | 04-May-26 | ABC Civil | 08-May-26 | Closed | 08-May-26 | Drain cleared
SNL-006 | Bedroom 2 | 1 | Painting | Wall damp patch (20x20cm) | High | Site Engr | 05-May-26 | XYZ Painters | 12-May-26 | In Progress |  | Waterproofing check ongoing
SNL-007 | Staircase | G | Civil | Handrail loose at 3rd baluster | Medium | Safety | 05-May-26 | ABC Civil | 09-May-26 | Closed | 09-May-26 | Fixed & tested
SNL-008 | Terrace | 3 | Civil | Terrace drain slope incorrect | High | Site Engr | 06-May-26 | ABC Civil | 15-May-26 | Open |  | Major rectification
SNL-009 | All Bathrooms | G | Plumbing | Flush pressure low | Medium | Client | 07-May-26 | AquaFit | 12-May-26 | In Progress |  | Pressure regulator being adjusted
SNL-010 | Main Door | G | Carpentry | Door not closing flush | Medium | QC | 08-May-26 | Carpenter | 12-May-26 | Open
SNL-011 | Electrical DB | G | Electrical | DB label missing on 4 breakers | Low | Safety | 08-May-26 | PowerTech | 11-May-26 | Closed | 10-May-26 | Labels fixed
SNL-012 | Kitchen | G | Plumbing | Under-sink pipe joint seeping | High | Client | 09-May-26 | AquaFit | 13-May-26 | Open

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit