## Dashboard
Snag Close-Out Dashboard
Live close-out status — updates automatically from the Snag List sheet
Total Snags | Closed | Open | % Complete | Overdue | Avg Days Open
10 | 3 | 7 | 30% | 7 | 21.1
Close-out | Count
Closed | 3
Open | 7
Location | Snags
Ground Floor | 3
First Floor | 2
Second Floor | 2
Exterior | 1
Common Area | 2

## Snag List
Snag List with Status Dashboard
Track defects to close-out before handover — built for Microsoft Excel 2016+
# | Snag Description | Location | Trade | Severity | Raised Date | Target Date | Status | Closed Date | Days Open | Notes
1 | Cracked tile in lobby | Ground Floor | Civil | Medium | 2026-05-02 | 2026-05-12 | Closed | 2026-05-10 | 8
2 | Socket not working | First Floor | Electrical | High | 2026-05-03 | 2026-05-08 | Verified | 2026-05-07 | 4 | Re-tested OK
3 | Leaking tap | First Floor | Plumbing | Medium | 2026-05-05 | 2026-05-15 | Fixed | 2026-05-14 | 9 | Awaiting check
4 | AC not cooling | Second Floor | HVAC | High | 2026-05-06 | 2026-05-11 | In Progress |  | 35
5 | Paint scuff on wall | Second Floor | Painting | Low | 2026-05-08 | 2026-05-20 | Open |  | 33
6 | Door hinge loose | Common Area | Carpentry | Low | 2026-05-09 | 2026-05-18 | Open |  | 32
7 | Water seepage ceiling | Ground Floor | Civil | High | 2026-05-10 | 2026-05-16 | In Progress |  | 31 | Monitoring
8 | Light flickering | Exterior | Electrical | Medium | 2026-05-12 | 2026-05-22 | Open |  | 29
9 | Tile grout missing | Common Area | Civil | Low | 2026-05-14 | 2026-05-24 | Open |  | 27
10 | Drain blockage | Ground Floor | Plumbing | High | 2026-05-15 | 2026-05-19 | Verified | 2026-05-18 | 3 | Cleared
Formulas:
Days Open = IF([Raised Date]="","",IF([Closed Date]="",TODAY()-[Raised Date],[Closed Date]-[Raised Date]))

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit