## Toolbox Talk
SITE SAFETY TOOLBOX TALK REGISTER
Record every toolbox talk, topic covered, attendance and the safety observations raised.
Sr | Date | Topic | Presented By | Work Area | Contractor | Workers Present | Duration (Min) | Observations | Action Required | Signed Off
1 | 2026-01-05 | Working at Height and Fall Arrest | Sandeep Rao | Tower A - Level 8 | Shreeji Constructions | 42 | 20 | Two workers without full body harness | Yes | Yes
2 | 2026-01-06 | Safe Use of Power Tools | Prakash Ghadge | Fabrication Yard | Vinayak Fabricators | 28 | 15 | Grinder guard missing on one unit | Yes | Yes
3 | 2026-01-08 | Excavation and Trench Safety | Sandeep Rao | Basement Zone B | Shreeji Constructions | 35 | 25 | Shoring adequate no issue found | No | Yes
4 | 2026-01-12 | Electrical Safety and Lockout | Ramesh Solanki | Tower B - Level 3 | Vinayak Electricals | 24 | 20 | Temporary wiring left uncovered | Yes | Yes
5 | 2026-01-14 | Manual Handling and Lifting | Prakash Ghadge | Material Store | Sharma Roadways | 31 | 15 | Workers advised on lifting posture | No | Yes
6 | 2026-01-19 | Scaffolding Inspection Basics | Sandeep Rao | Tower A - Level 10 | Sunrise Scaffolds | 38 | 25 | Two loose planks reported | Yes | Yes
7 | 2026-01-21 | Fire Prevention and Hot Work | Mahesh Tandel | Welding Bay | Vinayak Fabricators | 22 | 20 | Fire watch not posted | Yes | Yes
8 | 2026-01-26 | Personal Protective Equipment | Prakash Ghadge | All Zones | All Contractors | 68 | 15 | Six workers without safety shoes | Yes | Yes
9 | 2026-02-02 | Crane and Lifting Operations | Sandeep Rao | Tower B - Podium | Liftwell Cranes | 26 | 30 | Load chart displayed correctly | No | Yes
10 | 2026-02-05 | Confined Space Entry | Mahesh Tandel | Water Tank Area | Aquapure Engineers | 14 | 30 | Gas testing record incomplete | Yes | Yes
11 | 2026-02-09 | Housekeeping and Waste Disposal | Prakash Ghadge | All Zones | All Contractors | 55 | 15 | Debris blocking one access route | Yes | Yes
12 | 2026-02-13 | Heat Stress and Hydration | Ramesh Solanki | Open Terrace | Shreeji Constructions | 44 | 15 | Water points to be increased | Yes | Yes
13 | 2026-02-17 | Emergency Evacuation Drill | Sandeep Rao | All Zones | All Contractors | 82 | 40 | Assembly point reached in 4 minutes | No | Yes
14 | 2026-02-20 | Barricading and Signage | Prakash Ghadge | Tower A - Level 12 | Shreeji Constructions | 29 | 15 | Signage missing at open edge | Yes | Yes
15 | 2026-02-24 | Chemical Handling and MSDS | Mahesh Tandel | Paint Store | Colourcraft Painters | 18 | 20 | MSDS sheets now displayed | No | Yes
16 | 2026-02-27 | Night Shift Safety Precautions | Ramesh Solanki | Tower B - Level 5 | Vinayak Electricals | 21 | 20 | Additional lighting requested | Yes | Yes
TOTAL |  | 16 toolbox talks |  |  |  | 577 | 340

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit