## Steel Consumption
STEEL REINFORCEMENT CONSUMPTION REGISTER
Reconcile TMT steel received vs consumed against BBS by diameter — ExcelGurukulOnline.com
Date | Bar Dia (mm) | Structure | Received (kg) | Consumed (kg) | Balance (kg) | Wastage (kg) | Wastage %
2026-06-02 | 8 | Slab – Ground | 2500 | 2350 | 150 | 90 | 3.83%
2026-06-03 | 10 | Columns – B1 | 1800 | 1720 | 80 | 60 | 3.488%
2026-06-04 | 12 | Beams – First floor | 3200 | 3080 | 120 | 110 | 3.571%
2026-06-06 | 16 | Footings | 4500 | 4300 | 200 | 150 | 3.488%
2026-06-08 | 20 | Raft – Basement | 6800 | 6550 | 250 | 200 | 3.053%
2026-06-10 | 8 | Slab – First floor | 2600 | 2480 | 120 | 95 | 3.831%
2026-06-12 | 10 | Staircase | 1500 | 1440 | 60 | 50 | 3.472%
2026-06-14 | 12 | Columns – F1 | 2900 | 2790 | 110 | 100 | 3.584%
2026-06-16 | 16 | Beams – Second floor | 3600 | 3450 | 150 | 130 | 3.768%
2026-06-18 | 20 | Retaining wall | 5200 | 5000 | 200 | 170 | 3.4%
2026-06-20 | 8 | Slab – Second floor | 2700 | 2600 | 100 | 85 | 3.269%
2026-06-22 | 12 | Lintels | 1400 | 1350 | 50 | 45 | 3.333%
2026-06-24 | 16 | Shear wall | 4100 | 3950 | 150 | 140 | 3.544%
2026-06-26 | 10 | Parapet | 900 | 860 | 40 | 35 | 4.07%
2026-06-28 | 20 | Water tank | 3400 | 3280 | 120 | 115 | 3.506%
TOTAL |  | TOTAL | 47100 | 45200 |  | 1575

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit