## Material Indent
SITE MATERIAL INDENT AND REQUISITION REGISTER
Log indents, quantity requested versus issued, balance pending and status ¦ ExcelGurukulOnline.com
Indent No | Date | Material | Unit | Qty Requested | Qty Issued | Balance | Status
IND-101 | 2026-06-01 | Cement OPC 53 | Bag | 50 | 50 | 0 | Closed
IND-102 | 2026-06-01 | Steel 12mm | Kg | 800 | 600 | 200 | Partial
IND-103 | 2026-06-02 | River Sand | Cft | 200 | 200 | 0 | Closed
IND-104 | 2026-06-02 | Bricks | Nos | 5000 | 5000 | 0 | Closed
IND-105 | 2026-06-03 | Aggregate 20mm | Cft | 150 | 100 | 50 | Partial
IND-106 | 2026-06-03 | Binding Wire | Kg | 40 | 40 | 0 | Closed
IND-107 | 2026-06-04 | Shuttering Ply | Sheet | 30 | 20 | 10 | Partial
IND-108 | 2026-06-04 | Cement OPC 43 | Bag | 30 | 0 | 30 | Open
IND-109 | 2026-06-05 | PVC Pipe 4inch | Rmt | 60 | 60 | 0 | Closed
IND-110 | 2026-06-05 | Electrical Conduit | Rmt | 120 | 90 | 30 | Partial
IND-111 | 2026-06-06 | Wall Putty | Bag | 25 | 25 | 0 | Closed
IND-112 | 2026-06-06 | Paint Primer | Ltr | 80 | 0 | 80 | Open
IND-113 | 2026-06-07 | Tiles 600x600 | Box | 45 | 45 | 0 | Closed
IND-114 | 2026-06-07 | Tile Adhesive | Bag | 20 | 15 | 5 | Partial
IND-115 | 2026-06-08 | Sanitary Fittings | Set | 8 | 8 | 0 | Closed

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit