## Event Timeline Run Sheet
Event Timeline / Run Sheet
ExcelGurukulOnline.com ¦ Event Planning & Management · Corporate Events
Time | Duration (Min) | Activity | Responsible | Location | AV Required? | Status | Notes
07:00 AM | 60 | Venue setup begins — AV, decor, tables | Event Manager | Ballroom A+B | Yes | Done | Checklist signed off
08:00 AM | 30 | Vendor check-in & briefing | Event Coord | Lobby | No | Done | All vendors on site
08:30 AM | 30 | Registration desk opens | Volunteers | Main Entrance | No | Done | Guest list loaded
09:00 AM | 30 | Delegates & guests arrive | Welcome Team | Lobby | Yes | Done | Ushers in position
09:30 AM | 15 | Welcome address — MC | MC Kiran | Main Stage | Yes | Done
09:45 AM | 20 | Opening keynote — Chief Guest | Kavita Singh | Main Stage | Yes | Done | 45 min speech planned
10:05 AM | 30 | Panel Discussion — Innovation in Tech | Moderator | Main Stage | Yes | Upcoming | 4 panellists confirmed
10:35 AM | 15 | Sponsor Recognition & Awards — Round 1 | Event Manager | Main Stage | Yes | Upcoming | Trophy table ready
10:50 AM | 30 | Networking Tea / Coffee Break | Catering Team | Foyer | No | Upcoming | 150 pax snacks
11:20 AM | 45 | Workshop Session A | Facilitator | Hall B | Yes | Upcoming | Projector + sound
12:05 PM | 60 | Lunch | Catering Team | Dining Hall | No | Upcoming | 250 pax lunch
01:05 PM | 45 | Product Launch Presentation | CEO | Main Stage | Yes | Upcoming | Video + live demo
01:50 PM | 30 | Q&A Session | Moderator | Main Stage | Yes | Upcoming | Roving mics ready
02:20 PM | 30 | Awards Ceremony — Round 2 | MC Kiran | Main Stage | Yes | Upcoming | 10 trophies
02:50 PM | 10 | Vote of Thanks | Organiser | Main Stage | Yes | Upcoming
03:00 PM | 60 | High Tea & Networking | Catering Team | Foyer | No | Upcoming | High tea snacks
04:00 PM | 60 | Venue clearing & vendor departure | Event Manager | All areas | No | Upcoming | Security to stay till 5pm

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit