## Team Building
Team Building Event Planner
Plan team offsite activities with schedule, facilitator, cost and materials checklist ¦ ExcelGurukulOnline.com
Activity | Date | Time Slot | Facilitator | Participants | Cost (INR) | Materials / Venue | Status
Welcome & Icebreakers | 2026-07-24 | 09:00 - 09:45 | HR Team | 48 | 5000 | Main lawn - name tags and music | Confirmed
Team Treasure Hunt | 2026-07-24 | 10:00 - 12:00 | EventPro Facilitators | 48 | 28000 | Resort grounds - clue kits | Confirmed
Group Lunch | 2026-07-24 | 12:30 - 13:30 | Resort Catering | 48 | 36000 | Banquet hall - buffet | Confirmed
Raft Building Challenge | 2026-07-24 | 14:00 - 16:00 | EventPro Facilitators | 48 | 42000 | Lakeside - barrels ropes planks | Confirmed
High Tea & Awards | 2026-07-24 | 16:30 - 17:30 | HR Team | 48 | 12000 | Lawn - trophies and certificates | Confirmed
Bonfire & Open Mic | 2026-07-24 | 19:30 - 21:30 | Internal Anchor | 48 | 15000 | Amphitheatre - sound system | Confirmed
Morning Yoga Session | 2026-07-25 | 07:00 - 08:00 | Wellness Coach | 30 | 8000 | Lawn - yoga mats | Confirmed
Leadership Workshop | 2026-07-25 | 09:30 - 11:30 | Guest Speaker - R. Malhotra | 48 | 50000 | Conference hall - projector | Confirmed
Cross-Team Quiz | 2026-07-25 | 11:45 - 12:45 | Internal Anchor | 48 | 6000 | Conference hall - buzzers | In Planning
Farewell Lunch | 2026-07-25 | 13:00 - 14:00 | Resort Catering | 48 | 34000 | Banquet hall - buffet | Confirmed
Return Travel | 2026-07-25 | 15:00 - 18:00 | Admin Team | 48 | 45000 | 2 AC coaches | Confirmed
Photography & Video | 2026-07-24 | Full Day | Lens Studio | 2 | 18000 | Both days coverage | Confirmed
First Aid & Safety Desk | 2026-07-24 | Full Day | Resort Medical | 2 | 4000 | First aid kits both days | Confirmed
Event T-Shirts & Caps | 2026-07-20 | Pre-event | Procurement | 48 | 26400 | Printed kits - size list | In Planning
Feedback Survey Rollout | 2026-07-27 | Post-event | HR Team | 48 | 0 | Online survey link | Planned
|  |  |  | TOTAL | 329400

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit