## Annual Day Planner
Annual Day Function Planner
Plan company annual day activities with budget actuals and variance
Activity | Owner | Vendor | Due Date | Budget (₹) | Actual (₹) | Variance (₹) | Status
Venue Booking | Admin Team | Grand Orchid Banquets | 2026-11-10 | 250000 | 245000 | 5000 | Booked
Stage and Backdrop | Admin Team | Creative Decorators | 2026-11-25 | 80000 | 85000 | -5000 | Confirmed
Sound and Lights | Events Committee | SoundWorks Pro | 2026-11-25 | 60000 | 58000 | 2000 | Confirmed
Catering (450 pax) | Admin Team | Sagar Caterers | 2026-12-01 | 315000 | 320000 | -5000 | Menu Finalised
Anchor and Emcee | HR Team | Talent Hub | 2026-11-30 | 25000 | 25000 | 0 | Confirmed
Cultural Performances | Events Committee | Internal Teams | 2026-12-05 | 40000 | 32000 | 8000 | Rehearsals On
Awards and Trophies | HR Team | Crown Trophies | 2026-11-20 | 55000 | 52000 | 3000 | Ordered
Photography and Video | Admin Team | PixelStory Studio | 2026-11-30 | 45000 | 45000 | 0 | Confirmed
Invitations and Passes | HR Team | PrintExpress | 2026-11-15 | 12000 | 10500 | 1500 | Delivered
Employee Gifts | HR Team | GiftKart | 2026-12-01 | 135000 | 140000 | -5000 | Ordered
Guest Speaker Honorarium | Leadership | Direct | 2026-12-10 | 50000 | 50000 | 0 | Confirmed
Transport Arrangements | Admin Team | City Travels | 2026-12-12 | 35000 | 30000 | 5000 | Planned
Standee and Branding | Marketing | AdPrint Media | 2026-11-28 | 20000 | 22000 | -2000 | In Progress
Games and Fun Zone | Events Committee | FunZone Events | 2026-12-05 | 30000 | 28000 | 2000 | Planned
Contingency | Finance | NA | 2026-12-12 | 40000 | 15000 | 25000 | Reserved
TOTAL |  |  |  | 1192000 | 1157500 | 34500

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit