## Namkaran Planner
Baby Naming Ceremony (Namkaran) Planner
Plan every task, vendor and cost for the baby naming ceremony from start to finish
Task/Item | Category | Assigned To | Vendor/Contact | Due Date | Estimated Cost (Rs) | Status | Notes
Finalise Auspicious Date and Muhurat | Planning | Grandparents | Family Priest | 2026-03-01 | 0 | Completed | Confirmed with pandit ji
Book Venue/Hall | Venue | Father | Sunrise Banquet Hall | 2026-03-05 | 45000 | Confirmed | Hall for 60 guests
Book Priest for Ceremony | Rituals | Grandparents | Pandit Sharma | 2026-03-05 | 5000 | Confirmed | Includes samagri
Order Naming Ceremony Decor | Decor | Mother | Petal Decor Studio | 2026-03-08 | 18000 | Confirmed | Pastel theme with baby cradle
Finalise Guest List | Guests | Parents | - | 2026-03-06 | 0 | Completed | 60 guests confirmed
Send Invitations | Guests | Mother | Print and WhatsApp | 2026-03-10 | 3000 | In Progress | Digital + printed cards
Order Baby Outfit for Ceremony | Shopping | Mother | Little Angels Boutique | 2026-03-09 | 4500 | Confirmed | Traditional silk outfit
Arrange Cradle Decoration | Decor | Grandmother | Petal Decor Studio | 2026-03-08 | 6000 | Confirmed | For jhula ceremony
Book Photographer | Photography | Father | Moments Studio | 2026-03-07 | 15000 | Confirmed | 4 hours coverage
Order Catering/Lunch | Catering | Father | Annapurna Caterers | 2026-03-10 | 60000 | Confirmed | Veg lunch for 60 guests
Arrange Return Gifts | Gifts | Mother | Gift Basket Co | 2026-03-12 | 9000 | In Progress | 60 return gift boxes
Order Naming Ceremony Cake | Catering | Mother | Sweet Treats Bakery | 2026-03-14 | 3500 | Pending | Baby themed cake
Arrange Family Accommodation | Logistics | Father | - | 2026-03-13 | 12000 | Confirmed | Out-of-town relatives
Prepare Name Announcement Board | Decor | Mother | Petal Decor Studio | 2026-03-14 | 2500 | Pending | Calligraphy name board
Arrange Music/Shehnai | Entertainment | Grandparents | Local Shehnai Group | 2026-03-15 | 8000 | Pending | During the ceremony
Final Walkthrough and Rehearsal | Planning | Parents | - | 2026-03-15 | 0 | Pending | One day before the event

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit