## Task Dependencies
Task Dependency Tracker
Track project task dependencies — predecessor tasks, dependency types, planned and actual dates, blockers, and status
S.No. | Task ID | Task Name | Owner | Depends On | Dep. Type | Planned Start | Planned End | Actual Start | Actual End | Days | Status | Blocker | Notes
1 | T-001 | Project Charter sign-off | PM | None | None | 2026-01-02 | 2026-01-05 | 2026-01-02 | 2026-01-05 | 3 | Done | No | Prerequisite for all tasks
2 | T-002 | Requirements workshop | BA | T-001 | FS | 2026-01-06 | 2026-01-10 | 2026-01-06 | 2026-01-10 | 5 | Done | No | Finish-Start dependency
3 | T-003 | System design document | Tech Lead | T-002 | FS | 2026-01-11 | 2026-01-18 | 2026-01-11 | 2026-01-18 | 8 | Done | No
4 | T-004 | Database schema design | DBA | T-002 | FS | 2026-01-11 | 2026-01-16 | 2026-01-11 | 2026-01-16 | 6 | Done | No | Parallel with T-003
5 | T-005 | UI/UX mockups | Designer | T-002 | FS | 2026-01-11 | 2026-01-17 | 2026-01-12 | 2026-01-18 | 7 | Done | No | 1 day delayed — minor
6 | T-006 | Dev environment setup | DevOps | T-003 | FS | 2026-01-19 | 2026-01-22 | 2026-01-19 | 2026-01-22 | 4 | Done | No
7 | T-007 | Backend API development | Dev Team | T-003,T-004 | FS | 2026-01-19 | 2026-02-07 | 2026-01-19 |  | 20 | In Progress | No | Critical path
8 | T-008 | Frontend development | Dev Team | T-005,T-006 | FS | 2026-01-20 | 2026-02-10 | 2026-01-20 |  | 22 | In Progress | No | Parallel with T-007
9 | T-009 | Integration development | Dev Lead | T-007,T-008 | FS | 2026-02-09 | 2026-02-18 |  |  | 10 | Pending | Yes | Blocked by T-007 and T-008
10 | T-010 | Unit testing | QA Team | T-007 | SS | 2026-01-26 | 2026-02-14 | 2026-01-26 |  | 20 | In Progress | No | Start-Start with T-007
11 | T-011 | Integration testing | QA Team | T-009 | FS | 2026-02-19 | 2026-02-28 |  |  | 10 | Pending | Yes | Blocked by T-009
12 | T-012 | UAT preparation | BA | T-010 | FS | 2026-02-16 | 2026-02-20 |  |  | 5 | Pending | No
13 | T-013 | User acceptance testing | Business | T-011,T-012 | FS | 2026-03-02 | 2026-03-13 |  |  | 12 | Pending | Yes | Depends on T-011 and T-012
14 | T-014 | Performance testing | QA Team | T-011 | FS | 2026-03-02 | 2026-03-09 |  |  | 8 | Pending | Yes | Parallel with T-013
15 | T-015 | Security pen test | IT Security | T-011 | FS | 2026-03-02 | 2026-03-06 |  |  | 5 | Pending | Yes
16 | T-016 | UAT sign-off | Business | T-013 | FS | 2026-03-16 | 2026-03-18 |  |  | 3 | Pending | Yes | Go-live gate
17 | T-017 | Production deployment | DevOps | T-014,T-015,T-016 | FS | 2026-03-23 | 2026-03-25 |  |  | 3 | Pending | Yes | All must complete first
18 | T-018 | User training delivery | L&D | T-012 | FS | 2026-03-09 | 2026-03-20 |  |  | 12 | Pending | No | Can start before UAT done
19 | T-019 | Go-live support | Dev+IT | T-017 | FS | 2026-03-25 | 2026-04-01 |  |  | 7 | Pending | Yes | Hypercare week
20 | T-020 | Project closure report | PM | T-019 | FS | 2026-04-02 | 2026-04-08 |  |  | 5 | Pending | Yes | Final deliverable

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit