## Rework Log
PROJECT REWORK TRACKING LOG
Track rework items, root cause, effort lost and preventive action during execution
Rework ID | Date Raised | Work Item | Root Cause | Raised By | Rework Hours | Cost Impact (₹) | Status
RW-001 | 2026-02-03 | Login Module | Unclear requirement | Ramesh | 8 | 12000 | Closed
RW-002 | 2026-02-05 | Report Layout | Design change | Priya | 5 | 7500 | Closed
RW-003 | 2026-02-08 | Data Import | Wrong mapping | Aakash | 12 | 18000 | Open
RW-004 | 2026-02-11 | API Integration | Version mismatch | Neha | 6 | 9000 | Open
RW-005 | 2026-02-14 | Dashboard KPI | Formula error | Ramesh | 3 | 4500 | Closed
RW-006 | 2026-02-17 | Payment Flow | Missing validation | Priya | 10 | 15000 | Open
RW-007 | 2026-02-20 | Email Alerts | Config gap | Vikram | 4 | 6000 | Closed
RW-008 | 2026-02-23 | Search Feature | Ambiguous scope | Neha | 7 | 10500 | Open
RW-009 | 2026-02-26 | User Roles | Late feedback | Aakash | 5 | 7500 | Closed
RW-010 | 2026-03-02 | Export to PDF | Library bug | Ramesh | 6 | 9000 | Open
RW-011 | 2026-03-05 | Notification | Duplicate logic | Priya | 3 | 4500 | Closed
RW-012 | 2026-03-08 | Audit Trail | Spec change | Vikram | 8 | 12000 | Open
RW-013 | 2026-03-11 | Mobile View | CSS issue | Neha | 4 | 6000 | Closed
RW-014 | 2026-03-14 | Data Sync | Timing bug | Aakash | 9 | 13500 | Open
RW-015 | 2026-03-17 | Login Timeout | Config error | Ramesh | 2 | 3000 | Closed
RW-016 | 2026-03-20 | Invoice PDF | Template change | Priya | 5 | 7500 | Open
|  | TOTAL |  |  | 97 | 145500

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit