## RAID Log
PROJECT RAID LOG TRACKER
Single log of Risks, Assumptions, Issues and Dependencies with owner, due date and status
ID | Type | Description | Impact | Owner | Due Date | Status
R-01 | Risk | Key vendor may miss delivery deadline | High | Procurement Lead | 2026-06-20 | Open
R-02 | Risk | Currency fluctuation on imported parts | Medium | Finance Lead | 2026-06-30 | Open
A-01 | Assumption | Client will provide test data by week 3 | Medium | Business Analyst | 2026-06-15 | Confirmed
A-02 | Assumption | Infra environment ready before UAT | High | IT Manager | 2026-06-25 | Open
I-01 | Issue | UAT server performance below target | High | Tech Lead | 2026-06-12 | In Progress
I-02 | Issue | Two developers on unplanned leave | Medium | Project Manager | 2026-06-10 | In Progress
D-01 | Dependency | Payment module depends on bank API | High | Integration Lead | 2026-06-28 | Open
D-02 | Dependency | Go-live depends on security sign-off | High | Security Lead | 2026-06-30 | Open
R-03 | Risk | Scope creep from new stakeholder asks | Medium | Project Manager | 2026-06-22 | Open
A-03 | Assumption | Budget approved for phase 2 | Low | Sponsor | 2026-07-01 | Open
I-03 | Issue | Requirement conflict in reporting module | Medium | Business Analyst | 2026-06-14 | Resolved
D-03 | Dependency | Training depends on user manual sign-off | Low | Documentation Lead | 2026-07-05 | Open
R-04 | Risk | Third-party licence renewal delay | Low | Procurement Lead | 2026-07-08 | Open
I-04 | Issue | Data migration mismatch found | High | Data Lead | 2026-06-11 | In Progress
D-04 | Dependency | Reporting relies on data warehouse load | Medium | Data Lead | 2026-07-02 | Open
A-04 | Assumption | No major regulatory change during build | Medium | Compliance Lead | 2026-06-30 | Confirmed

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit