## Success Criteria
Project Success Criteria Register
Define measurable success criteria with targets, owners and sign-off status ¦ ExcelGurukulOnline.com
S.No. | Criteria ID | Success Criterion | Category | Measure | Target | Owner | Agreed On | Status
1 | SC-001 | Go-live within schedule | Schedule | Days variance | 0 days | Amit Sharma | 2026-01-08 | Agreed
2 | SC-002 | Stay within approved budget | Cost | Budget variance | <= 5% | Priya Nair | 2026-01-23 | Agreed
3 | SC-003 | User adoption after rollout | Adoption | Active users | 80% | Rahul Verma | 2026-02-06 | Agreed
4 | SC-004 | Defects at handover | Quality | Open defects | < 10 | Sneha Iyer | 2026-02-25 | Agreed
5 | SC-005 | Stakeholder satisfaction | Quality | Survey score | 4 of 5 | Vikram Singh | 2026-03-12 | Draft
6 | SC-006 | Training completion | Adoption | Staff trained | 100% | Anita Desai | 2026-03-27 | Agreed
7 | SC-007 | System uptime post go-live | Quality | Uptime | 99.5% | Karan Mehta | 2026-04-13 | Agreed
8 | SC-008 | Process cycle time reduced | Benefit | Cycle time | -20% | Divya Rao | 2026-04-28 | Draft
9 | SC-009 | Manual effort reduced | Benefit | Hours saved | 300 hrs | Sanjay Gupta | 2026-05-14 | Agreed
10 | SC-010 | Data migration accuracy | Quality | Records matched | 99.9% | Meera Joshi | 2026-05-29 | Agreed
11 | SC-011 | Vendor SLA compliance | Quality | SLA met | 95% | Arjun Patel | 2026-06-17 | Agreed
12 | SC-012 | Support tickets in month 1 | Quality | Tickets | < 50 | Pooja Reddy | 2026-07-02 | Draft
13 | SC-013 | Revenue impact year 1 | Benefit | Added revenue | AED 500K | Nikhil Bose | 2026-07-16 | Draft
14 | SC-014 | Compliance sign-off | Compliance | Audit passed | Yes | Ritu Malhotra | 2026-08-01 | Agreed
15 | SC-015 | Zero safety incidents | Compliance | Incidents | 0 | Suresh Kumar | 2026-08-18 | Agreed
16 | SC-016 | Customer complaints | Quality | Complaints | < 5 | Neha Kapoor | 2026-09-05 | Agreed
17 | SC-017 | Report automation coverage | Benefit | Reports automated | 12 | Manoj Pillai | 2026-09-19 | Draft
18 | SC-018 | Legacy system retired | Schedule | Cutover done | Yes | Kavita Menon | 2026-10-06 | Agreed
19 | SC-019 | Knowledge transfer complete | Adoption | Sessions held | 6 | Rohit Saxena | 2026-10-20 | Agreed
20 | SC-020 | Benefits review scheduled | Benefit | Review booked | Yes | Shalini Das | 2026-11-06 | Draft

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit