## Benefits Realisation
Project Benefits Realisation Plan
Define expected project benefits with baseline target measurement method and realisation date.
Benefit | Type | Baseline | Target | Improvement | Unit | Measure Method | Owner | Realisation Date | Confidence
Order processing time | Efficiency | 48 | 18 | 62.5% | Hours | System report | Ops Head | 2026-12-31 | High
Manual data entry effort | Efficiency | 1200 | 300 | 75% | Hours/Month | Timesheet | Ops Head | 2026-11-30 | High
Invoice error rate | Quality | 6.5 | 1.5 | 76.92% | Percent | Audit sample | Finance Head | 2027-03-31 | Medium
Customer onboarding days | Experience | 21 | 7 | 66.67% | Days | CRM report | Sales Head | 2026-10-31 | High
Support ticket backlog | Service | 480 | 120 | 75% | Tickets | Helpdesk | Support Lead | 2026-09-30 | Medium
Inventory carrying cost | Financial | 7200000 | 5400000 | 25% | INR/Year | ERP report | Supply Head | 2027-03-31 | Medium
Stock out incidents | Service | 34 | 8 | 76.47% | Count/Quarter | ERP report | Supply Head | 2026-12-31 | High
Report preparation time | Efficiency | 96 | 24 | 75% | Hours/Month | Timesheet | MIS Lead | 2026-11-30 | High
Compliance findings | Risk | 14 | 3 | 78.57% | Count/Year | Audit report | Compliance | 2027-03-31 | Low
Vendor payment delays | Financial | 22 | 5 | 77.27% | Days | ERP report | Finance Head | 2027-01-31 | Medium
Staff training hours | Capability | 8 | 24 | 200% | Hours/Year | LMS report | HR Head | 2026-12-31 | High
System downtime | Availability | 18 | 4 | 77.78% | Hours/Quarter | Monitoring | IT Head | 2026-10-31 | High
Paper consumption | Sustainability | 240 | 60 | 75% | Reams/Year | Purchase log | Admin Head | 2027-03-31 | Medium
Duplicate master records | Quality | 1850 | 200 | 89.19% | Count | Data audit | MIS Lead | 2026-12-31 | Medium
Revenue leakage | Financial | 4200000 | 900000 | 78.57% | INR/Year | Finance audit | Finance Head | 2027-03-31 | Low
Employee satisfaction | Capability | 62 | 80 | 29.03% | Score | Survey | HR Head | 2027-03-31 | Medium

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit