## Change Request Log
PROJECT CHANGE REQUEST LOG
Track scope changes, cost and schedule impact, approval status — ExcelGurukulOnline.com
CR No | Date Raised | Raised By | Change Description | Priority | Cost Impact (₹) | Schedule Impact (Days) | Status | Approved By
CR-001 | 2026-01-06 | Client | Add SMS notification module | High | 120000 | 7 | Approved | Sponsor
CR-002 | 2026-01-11 | QA Lead | Extra security testing cycle | Medium | 65000 | 4 | Approved | PM
CR-003 | 2026-01-18 | Business | Change report layout | Low | 15000 | 1 | Approved | PM
CR-004 | 2026-02-02 | Client | Integrate payment gateway | High | 250000 | 12 | Under Review | -
CR-005 | 2026-02-09 | Dev Lead | Upgrade database version | Medium | 40000 | 3 | Approved | Tech Head
CR-006 | 2026-02-15 | Client | Add regional language | High | 180000 | 10 | Rejected | Sponsor
CR-007 | 2026-02-22 | Support | Additional user training batch | Low | 20000 | 2 | Approved | PM
CR-008 | 2026-03-03 | Client | Modify approval workflow | Medium | 55000 | 3 | Under Review | -
CR-009 | 2026-03-09 | Architect | Move to microservices | High | 320000 | 18 | On Hold | -
CR-010 | 2026-03-16 | Client | Change branding colours | Low | 8000 | 1 | Approved | PM
CR-011 | 2026-03-23 | QA Lead | Add automated regression | Medium | 90000 | 6 | Approved | Tech Head
CR-012 | 2026-04-01 | Business | New MIS dashboard | High | 140000 | 8 | Under Review | -
CR-013 | 2026-04-08 | Client | Extend warranty period | Low | 30000 | 0 | Approved | Sponsor
CR-014 | 2026-04-15 | Dev Lead | Refactor legacy module | Medium | 75000 | 5 | Rejected | PM
CR-015 | 2026-04-22 | Client | Add two-factor login | High | 95000 | 4 | Approved | Sponsor
CR-016 | 2026-04-29 | Support | Improve error messages | Low | 12000 | 1 | Approved | PM
TOTAL |  |  | APPROVED / TOTAL COST IMPACT |  | 1515000 | 85

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit