## Earned Value
EARNED VALUE ANALYSIS TRACKER
Track PV, EV and AC to derive CPI and SPI and flag cost or schedule slippage early.
Task / Work Package | Planned Value (₹) | Earned Value (₹) | Actual Cost (₹) | CPI | SPI | Status
Requirements | 200000 | 200000 | 190000 | 1.0526 | 1 | On Track
Design | 300000 | 285000 | 300000 | 0.95 | 0.95 | Watch
Build Module A | 450000 | 430000 | 470000 | 0.91489 | 0.95556 | Over Cost
Build Module B | 400000 | 410000 | 395000 | 1.038 | 1.025 | Ahead
Integration | 250000 | 220000 | 260000 | 0.84615 | 0.88 | Behind
Testing | 300000 | 280000 | 290000 | 0.96552 | 0.93333 | On Track
UAT | 180000 | 175000 | 182000 | 0.96154 | 0.97222 | On Track
Deployment | 150000 | 140000 | 155000 | 0.90323 | 0.93333 | Watch
Training | 120000 | 120000 | 110000 | 1.0909 | 1 | Ahead
Documentation | 90000 | 80000 | 95000 | 0.84211 | 0.88889 | Behind
Data Migration | 220000 | 210000 | 225000 | 0.93333 | 0.95455 | Watch
Security Review | 140000 | 130000 | 138000 | 0.94203 | 0.92857 | On Track
Performance Test | 110000 | 105000 | 112000 | 0.9375 | 0.95455 | On Track
Cutover | 160000 | 150000 | 168000 | 0.89286 | 0.9375 | Over Cost
Hypercare | 130000 | 125000 | 128000 | 0.97656 | 0.96154 | On Track
Closure | 80000 | 80000 | 78000 | 1.0256 | 1 | Ahead
TOTAL | 3280000 | 3140000 | 3296000

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit