## Contingency Reserve Tracker
Project Contingency Reserve Tracker
Track approved contingency reserve against amounts drawn by category
Date | Reserve Category | Approved Reserve (INR) | Amount Drawn (INR) | Remaining Reserve (INR) | Reason for Drawdown | Approved By
2026-01-03 | Design Change Reserve | 200000 | 45000 | 155000 | Scope revision on UI module | Finance Controller
2026-01-09 | Technical Risk Reserve | 300000 | 0 | 300000 |  | Finance Controller
2026-01-15 | Schedule Delay Reserve | 250000 | 60000 | 190000 | Vendor delivery delay | Finance Controller
2026-01-22 | Resource Backup Reserve | 150000 | 30000 | 120000 | Emergency contractor hire | Finance Controller
2026-01-28 | Material Price Escalation Reserve | 180000 | 25000 | 155000 | Steel price hike | Finance Controller
2026-02-05 | Design Change Reserve | 200000 | 70000 | 130000 | Additional client change request | Finance Controller
2026-02-11 | Technical Risk Reserve | 300000 | 50000 | 250000 | Integration rework | Finance Controller
2026-02-18 | Schedule Delay Reserve | 250000 | 90000 | 160000 | Permit approval delay | Finance Controller
2026-02-24 | Resource Backup Reserve | 150000 | 45000 | 105000 | Replacement of resigned staff | Finance Controller
2026-03-02 | Regulatory Compliance Reserve | 120000 | 20000 | 100000 | Additional certification fee | Finance Controller
2026-03-10 | Material Price Escalation Reserve | 180000 | 40000 | 140000 | Cement price increase | Finance Controller
2026-03-16 | Technical Risk Reserve | 300000 | 80000 | 220000 | Server migration issue | Finance Controller
2026-03-21 | Design Change Reserve | 200000 | 90000 | 110000 | Final scope adjustment | Finance Controller
2026-03-27 | Schedule Delay Reserve | 250000 | 110000 | 140000 | Extended testing cycle | Finance Controller
2026-04-03 | Regulatory Compliance Reserve | 120000 | 35000 | 85000 | Local authority inspection fee | Finance Controller
2026-04-09 | Resource Backup Reserve | 150000 | 55000 | 95000 | Overtime for critical milestone | Finance Controller
TOTAL |  | 3300000 | 845000 | 2455000

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit