## Risk Register
Risk Register
Comprehensive risk register with probability, impact and mitigation planning
Risk ID | Risk Description | Category | Probability | Impact | Risk Score | Response | Mitigation Action | Owner | Status | Review Date
R-001 | Key resource leaves during execution | Resource | High | High | 9 | Mitigate | Cross-train backup resource; document knowledge | PM | Open | 2026-06-01
R-002 | Scope creep from stakeholders | Scope | High | High | 9 | Avoid | Enforce change control process; strict scope sign-off | PM | Open | 2026-06-01
R-003 | Budget overrun due to vendor pricing | Financial | Medium | High | 6 | Mitigate | Fix-price contracts; 15% contingency reserve | Finance | Open | 2026-06-01
R-004 | Technology integration delays | Technical | Medium | High | 6 | Mitigate | Early integration testing; vendor SLA penalties | IT Lead | Open | 2026-06-15
R-005 | Regulatory compliance changes | External | Low | High | 4 | Accept | Monitor regulatory updates; legal team on standby | Legal | Watch | 2026-07-01
R-006 | Delayed stakeholder approvals | Schedule | High | Medium | 6 | Mitigate | Define approval SLAs; escalation path agreed | PM | Open | 2026-06-01
R-007 | Data migration errors | Technical | Medium | High | 6 | Mitigate | Data validation scripts; parallel run period | IT Lead | Open | 2026-06-15
R-008 | Vendor delivery failure | External | Low | High | 4 | Transfer | Penalty clauses in contract; backup vendor identified | Procurement | Watch | 2026-07-01
R-009 | Security vulnerability in system | Technical | Low | Critical | 6 | Mitigate | Security audit pre-launch; pen testing | IT Lead | Open | 2026-06-15
R-010 | Change resistance from users | People | Medium | Medium | 4 | Mitigate | Change management plan; training and communication | HR | Open | 2026-06-01

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit