## Resource Plan
Project Resource Plan
Plan and track project resource allocation by month — internal and external resources, daily rates, H1 costs, and confirmation status
S.No. | Resource Name | Role | Type | Department | Jan | Feb | Mar | Apr | May | Jun | H1 Days | Day Rate (AED) | H1 Cost (AED) | Status | Notes
1 | Ahmed Al Rashid | Project Manager | Internal | IT | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 0 | 0 | Confirmed | Full time — dedicated PM
2 | Priya Sharma | Business Analyst | Internal | Marketing | 10 | 15 | 15 | 10 | 10 | 10 | 70 | 0 | 0 | Confirmed | 50-75% allocation
3 | Hassan Ali | Tech Lead | Internal | IT | 20 | 20 | 20 | 15 | 15 | 10 | 100 | 0 | 0 | Confirmed | Reducing after design phase
4 | Ravi Shankar | Senior Developer | Internal | IT | 5 | 20 | 20 | 20 | 20 | 15 | 100 | 0 | 0 | Confirmed | Ramping up from Feb
5 | Contractor 1 | Developer | External | IT | 0 | 20 | 20 | 20 | 20 | 20 | 100 | 1200 | 120000 | Approved | Contractor — start Feb
6 | Contractor 2 | QA Engineer | External | IT | 0 | 0 | 10 | 20 | 20 | 15 | 65 | 900 | 58500 | Approved | QA starts Mar
7 | Fatima Hassan | HR Liaison | Internal | HR | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 0 | 0 | Confirmed | 10-15% — part time support
8 | Suresh Mehta | Finance Sponsor | Internal | Finance | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 0 | 0 | Confirmed | Governance role — minimal time
9 | Legal Counsel | Legal Advisor | External | Legal | 2 | 1 | 1 | 1 | 1 | 1 | 7 | 1500 | 10500 | Approved | Contract review and advice
10 | Training Partner | L&D Specialist | External | L&D | 0 | 0 | 0 | 5 | 10 | 5 | 20 | 800 | 16000 | Planned | Training delivery Q2
11 | Sara Al Noor | Change Manager | Internal | Sales | 5 | 10 | 10 | 15 | 15 | 10 | 65 | 0 | 0 | Confirmed | Change management
12 | Omar Qureshi | Ops SME | Internal | Operations | 5 | 5 | 10 | 10 | 5 | 5 | 40 | 0 | 0 | Confirmed | Subject matter expert
13 | Divya Singh | Comms Lead | Internal | Marketing | 3 | 5 | 5 | 5 | 5 | 3 | 26 | 0 | 0 | Confirmed | Communications and updates
14 | DevOps Engineer | DevOps | External | IT | 0 | 5 | 5 | 10 | 10 | 5 | 35 | 1100 | 38500 | Approved | Infrastructure setup
15 | UX Designer | Designer | External | IT | 0 | 10 | 10 | 5 | 0 | 0 | 25 | 950 | 23750 | Planned | UI/UX design phase only
16 | Data Architect | Data Lead | External | IT | 5 | 10 | 10 | 5 | 5 | 0 | 35 | 1300 | 45500 | Approved | Data migration specialist
17 | Nadia Hassan | HR Training Lead | Internal | HR | 0 | 0 | 0 | 5 | 10 | 5 | 20 | 0 | 0 | Planned | End user training support
18 | Tom Baker | Ops SME 2 | Internal | Operations | 2 | 2 | 5 | 5 | 5 | 2 | 21 | 0 | 0 | Planned | Warehouse process expert
19 | Security Auditor | Pen Tester | External | Security | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 2000 | 10000 | Planned | One-time security audit
20 | Project Office | PMO Support | Internal | PMO | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 0 | 0 | Confirmed | PMO governance support

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit