## Resource Allocation
PROJECT RESOURCE ALLOCATION PLAN
Plan team allocation across tasks with daily cost and total effort cost
Resource | Role | Task | Allocation (%) | Start | End | Cost/Day (₹) | Total Cost (₹) | Status
A. Rao | PM | Planning | 50 | 2026-06-01 | 2026-06-30 | 6000 | 87000 | Active
B. Shah | BA | Requirements | 80 | 2026-06-01 | 2026-06-15 | 4500 | 50400 | Active
C. Iyer | Dev Lead | Architecture | 60 | 2026-06-05 | 2026-06-25 | 7000 | 84000 | Active
D. Khan | Developer | Module A | 100 | 2026-06-08 | 2026-06-28 | 4000 | 80000 | Active
E. Das | Developer | Module B | 100 | 2026-06-08 | 2026-06-28 | 4000 | 80000 | Active
F. Nair | QA | Testing | 70 | 2026-06-18 | 2026-07-05 | 3500 | 41650 | Planned
G. Menon | Designer | UI/UX | 50 | 2026-06-03 | 2026-06-20 | 5000 | 42500 | Active
H. Bose | DevOps | CI/CD | 40 | 2026-06-10 | 2026-06-30 | 6500 | 52000 | Active
I. Reddy | DBA | Database | 30 | 2026-06-06 | 2026-06-22 | 5500 | 26400 | Active
J. Pillai | Tech Writer | Docs | 40 | 2026-06-20 | 2026-07-08 | 3000 | 21600 | Planned
K. Gupta | Support | UAT Support | 60 | 2026-06-25 | 2026-07-10 | 2800 | 25200 | Planned
L. Joshi | Scrum Master | Ceremonies | 30 | 2026-06-01 | 2026-06-30 | 5000 | 43500 | Active
M. Verma | Developer | Integration | 100 | 2026-06-15 | 2026-07-02 | 4200 | 71400 | Planned
N. Singh | Analyst | Reporting | 50 | 2026-06-12 | 2026-06-28 | 3800 | 30400 | Active
O. Khan | PM | Risk Mgmt | 20 | 2026-06-01 | 2026-06-30 | 6000 | 34800 | Active
TOTAL | [6 empty] | 770850

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit