## Work Package Breakdown
Work Package Breakdown Sheet
Break the WBS into work packages with effort, cost, owner and schedule for planning-phase baselining
WBS Code | Work Package | Owner | Start Date | End Date | Effort (Days) | Cost Estimate | Deliverable
1.1 | Requirement workshops | Business Analyst | 2026-08-03 | 2026-08-14 | 10 | 150000 | Signed-off BRD
1.2 | Process mapping | Business Analyst | 2026-08-10 | 2026-08-21 | 8 | 120000 | As-is and to-be maps
2.1 | Solution architecture | Solution Architect | 2026-08-17 | 2026-08-28 | 10 | 200000 | Architecture document
2.2 | Data model design | Data Lead | 2026-08-24 | 2026-09-04 | 8 | 140000 | Approved data model
2.3 | Integration design | Solution Architect | 2026-08-31 | 2026-09-11 | 8 | 160000 | Interface specs
3.1 | Module build - Finance | Dev Team A | 2026-09-07 | 2026-10-02 | 20 | 400000 | Unit-tested module
3.2 | Module build - Inventory | Dev Team B | 2026-09-07 | 2026-10-02 | 20 | 400000 | Unit-tested module
3.3 | Module build - Reports | Dev Team A | 2026-10-05 | 2026-10-23 | 15 | 300000 | Report pack
3.4 | Integration build | Dev Team B | 2026-10-05 | 2026-10-23 | 15 | 320000 | Working interfaces
4.1 | System testing | QA Lead | 2026-10-26 | 2026-11-13 | 15 | 220000 | Test summary report
4.2 | UAT support | QA Lead | 2026-11-16 | 2026-11-27 | 10 | 150000 | UAT sign-off
5.1 | Data migration | Data Lead | 2026-11-23 | 2026-12-04 | 10 | 180000 | Migrated master data
5.2 | End-user training | Training Lead | 2026-11-30 | 2026-12-11 | 10 | 130000 | Trained user base
5.3 | Cutover and go-live | Project Manager | 2026-12-14 | 2026-12-18 | 5 | 100000 | Go-live sign-off
5.4 | Hypercare support | Dev Team A | 2026-12-21 | 2027-01-15 | 18 | 250000 | Stabilised system
TOTAL |  |  |  |  | 182 | 3220000

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit