## Procurement Plan
Project Procurement Plan
Plan project procurement with RFQ PO delivery dates lead time and cost
Item / Service | Category | Vendor | RFQ Date | PO Date | Delivery Date | Lead Time (Days) | Est. Cost (₹) | Status
Application Servers (4 nos) | Hardware | Dell India | 2026-02-02 | 2026-02-16 | 2026-03-20 | 32 | 1850000 | Delivered
Network Switches | Hardware | Cisco Partner | 2026-02-02 | 2026-02-20 | 2026-03-25 | 33 | 620000 | Delivered
Database Licences | Software | Oracle India | 2026-02-10 | 2026-03-01 | 2026-03-10 | 9 | 950000 | Delivered
Middleware Licences | Software | IBM Partner | 2026-02-10 | 2026-03-05 | 2026-03-15 | 10 | 480000 | Delivered
Firewall Appliance | Hardware | Fortinet Partner | 2026-02-15 | 2026-03-10 | 2026-04-12 | 33 | 380000 | Delivered
Testing Tools Licence | Software | Micro Focus | 2026-03-01 | 2026-03-20 | 2026-03-28 | 8 | 260000 | Delivered
Cloud Hosting (Year 1) | Services | AWS | 2026-03-05 | 2026-03-25 | 2026-04-01 | 7 | 1440000 | Active
UI/UX Design Services | Services | PixelCraft Studio | 2026-03-10 | 2026-04-01 | 2026-06-30 | 90 | 550000 | In Progress
Security Audit (VAPT) | Services | SecureNet Labs | 2026-04-01 | 2026-05-02 | 2026-07-15 | 74 | 320000 | In Progress
Training Content Development | Services | LearnWell | 2026-04-15 | 2026-05-15 | 2026-08-10 | 87 | 280000 | In Progress
Data Migration Services | Services | DataBridge | 2026-05-01 | 2026-06-01 | 2026-08-31 | 91 | 680000 | PO Released
Backup Solution | Hardware | Veeam Partner | 2026-05-10 | 2026-06-15 | 2026-07-30 | 45 | 420000 | PO Released
Load Testing Services | Services | PerfTest Co | 2026-06-01 | 2026-07-10 | 2026-09-15 | 67 | 180000 | RFQ Floated
AMC - Year 1 | Services | Dell India | 2026-07-01 | 2026-08-01 | 2026-09-30 | 60 | 240000 | RFQ Floated
Go-Live War Room Setup | Services | Admin | 2026-08-01 | 2026-09-01 | 2026-10-10 | 39 | 90000 | Planned
TOTAL | [6 empty] | 8740000

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit