## Procurement Plan
Procurement Planning Schedule
Plan project procurement packages with lead times required-on-site dates and tender milestones.
Package | Description | Category | Estimated Value (INR) | Lead Time (Days) | Required On Site | Tender Float | PO Target | Status
PKG-01 | Civil Works | Works | 8500000 | 120 | 2026-11-02 | 2026-06-05 | 2026-07-05 | Float Overdue
PKG-02 | Structural Steel | Materials | 6200000 | 90 | 2026-10-05 | 2026-06-07 | 2026-07-07 | Float Overdue
PKG-03 | Electrical Fitout | Works | 4800000 | 75 | 2026-11-16 | 2026-08-03 | 2026-09-02 | Float Now
PKG-04 | HVAC System | Equipment | 7400000 | 150 | 2026-12-07 | 2026-06-10 | 2026-07-10 | Float Overdue
PKG-05 | Fire Safety System | Equipment | 2900000 | 100 | 2026-11-23 | 2026-07-16 | 2026-08-15 | Float Overdue
PKG-06 | Plumbing Works | Works | 2100000 | 60 | 2026-10-19 | 2026-07-21 | 2026-08-20 | Float Now
PKG-07 | Flooring and Finishes | Materials | 3600000 | 70 | 2026-12-14 | 2026-09-05 | 2026-10-05 | Planned
PKG-08 | Elevators | Equipment | 9200000 | 180 | 2027-01-11 | 2026-06-15 | 2026-07-15 | Float Overdue
PKG-09 | IT Cabling | Works | 1800000 | 45 | 2026-12-21 | 2026-10-07 | 2026-11-06 | Planned
PKG-10 | Security Systems | Equipment | 2400000 | 90 | 2027-01-04 | 2026-09-06 | 2026-10-06 | Planned
PKG-11 | Furniture | Materials | 3100000 | 80 | 2027-01-18 | 2026-09-30 | 2026-10-30 | Planned
PKG-12 | Landscaping | Works | 1500000 | 50 | 2027-02-01 | 2026-11-13 | 2026-12-13 | Planned
PKG-13 | Generator Set | Equipment | 4100000 | 120 | 2026-12-28 | 2026-07-31 | 2026-08-30 | Float Now
PKG-14 | Water Treatment | Equipment | 2700000 | 110 | 2027-01-25 | 2026-09-07 | 2026-10-07 | Planned
PKG-15 | Signage | Materials | 800000 | 40 | 2027-02-08 | 2026-11-30 | 2026-12-30 | Planned
PKG-16 | Facade Glazing | Works | 5600000 | 130 | 2026-12-14 | 2026-07-07 | 2026-08-06 | Float Overdue
TOTAL |  |  | 66700000
Formulas:
Tender Float = [Required On Site]-[Lead Time (Days)]-30
PO Target = [Required On Site]-[Lead Time (Days)]
Status = IF([Tender Float]<TODAY(),"Float Overdue",IF([Tender Float]<=TODAY()+45,"Float Now","Planned"))

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit