## Quality Plan
PROJECT QUALITY MANAGEMENT PLAN
Define quality standards, metrics and control activities for each project deliverable
Deliverable | Quality Standard | Acceptance Criteria | Metric / Target | Review Method | Responsible | Frequency | Status
Requirements Document | IEEE 830 | Signed off by sponsor | 0 open gaps | Peer Review | Business Analyst | Once | Approved
Solution Design | Internal Design Std | Design walkthrough passed | 100% modules covered | Design Review | Solution Architect | Per module | In Progress
Test Plan | ISTQB | All scenarios mapped | 95% coverage | Inspection | QA Lead | Once | Draft
Code Base | Coding Guidelines | No critical defects | <5 defects/KLOC | Static Analysis | Tech Lead | Weekly | Ongoing
UAT Sign-Off | Business Rules | All UAT cases pass | 100% pass | User Testing | UAT Coordinator | Per cycle | Pending
Deployment Package | Release Checklist | Checklist complete | 0 blockers | Audit | Release Manager | Per release | Pending
User Manual | Documentation Std | Reviewed & readable | 0 major edits | Review | Tech Writer | Once | Draft
Training Material | L&D Standard | Feedback score >4/5 | Score >=4.0 | Feedback | Trainer | Per batch | Planned
Data Migration | Data Quality Rules | Reconciliation matched | 100% records | Reconciliation | Data Lead | Per run | Planned
Performance Test | NFR Spec | Response < 2 sec | P95 < 2s | Load Test | Perf Engineer | Per build | Planned
Security Review | OWASP Top 10 | No high findings | 0 high risks | VAPT | Security Lead | Per release | Planned
Handover Doc | Ops Standard | Ops accepted | 0 open items | Review | Project Manager | Once | Planned
Change Requests | Change Policy | Impact assessed | 100% assessed | CAB Review | Change Manager | Weekly | Ongoing
Status Reports | Reporting Std | Accurate & timely | On-time 100% | Review | PMO | Weekly | Ongoing
Risk Register | Risk Policy | Reviewed & updated | Reviewed weekly | Review | Risk Owner | Weekly | Ongoing
Closure Report | PM Methodology | Lessons captured | Sign-off obtained | Review | Project Manager | Once | Planned

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit