## Resource Leveling
Resource Leveling and Allocation Planner
project-management ¦ Track weekly resource allocation against availability to spot overloaded team members
| Resource Name | Role | Project | Allocated Hrs/Week | Available Hrs/Week | Utilization % | Status
| Anjali Mehra | Business Analyst | ERP Rollout | 36 | 40 | 90% | Near Capacity
| Rohit Sharma | Backend Developer | Customer Portal | 44 | 40 | 110% | Overallocated
| Priya Nair | UI/UX Designer | Mobile App Revamp | 30 | 40 | 75% | Available
| Karan Kapoor | QA Engineer | ERP Rollout | 38 | 40 | 95% | Near Capacity
| Sneha Iyer | Project Coordinator | Customer Portal | 42 | 40 | 105% | Overallocated
| Vikram Singh | DevOps Engineer | Cloud Migration | 46 | 40 | 115% | Overallocated
| Neha Gupta | Data Analyst | Reporting Dashboard | 28 | 40 | 70% | Available
| Arjun Rao | Backend Developer | Cloud Migration | 40 | 40 | 100% | Near Capacity
| Divya Menon | Business Analyst | Reporting Dashboard | 32 | 40 | 80% | Available
| Suresh Pillai | QA Engineer | Mobile App Revamp | 41 | 40 | 102.5% | Overallocated
| Kavita Joshi | Project Coordinator | ERP Rollout | 34 | 40 | 85% | Available
| Manish Verma | UI/UX Designer | Customer Portal | 39 | 40 | 97.5% | Near Capacity
| Ritu Malhotra | Data Analyst | Cloud Migration | 26 | 40 | 65% | Available
| Aditya Kumar | DevOps Engineer | Reporting Dashboard | 45 | 40 | 112.5% | Overallocated
| Pooja Bhatt | Business Analyst | Mobile App Revamp | 37 | 40 | 92.5% | Near Capacity
| Sanjay Reddy | Backend Developer | ERP Rollout | 43 | 40 | 107.5% | Overallocated

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit