## Property Inspection
Rental Property Inspection Log
Record detailed rental property inspection findings — condition, issues, severity, repair costs, and action required by area
S.No. | Property | Inspection Date | Type | Inspector | Area | Item Checked | Condition | Issue Found | Severity | Action Required | Tenant Informed | Repair Cost | Status
1 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Living Room | Walls and ceiling | Good | None | None | N/A | N/A | 0 | Clear
2 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Living Room | Floor and tiles | Good | Minor scratch near entrance | Low | Monitor at next inspection | Yes | 0 | Noted
3 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Kitchen | Sink and drainage | Good | Slow drain — partial block | Medium | Plumber to clear drain | Yes | 250 | Action Needed
4 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Kitchen | Exhaust fan | Fair | Noisy fan — bearing worn | Low | Replace fan bearing | Yes | 150 | Action Needed
5 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Bedroom 1 | AC unit | Good | None | None | N/A | N/A | 0 | Clear
6 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Bedroom 1 | Window and frame | Good | None | None | N/A | N/A | 0 | Clear
7 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Bedroom 2 | Walls | Fair | Scuff marks on one wall | Low | Note — charge on exit | Yes | 0 | Noted
8 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Bedroom 2 | AC unit | Good | Filter needs cleaning | Low | Clean filter — tenant to do | Yes | 0 | Noted
9 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Bathroom 1 | Toilet and flush | Good | None | None | N/A | N/A | 0 | Clear
10 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Bathroom 1 | Shower and faucet | Good | None | None | N/A | N/A | 0 | Clear
11 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Bathroom 2 | Tiles | Fair | 1 tile cracked near toilet | Medium | Replace tile — arrange | Yes | 200 | Action Needed
12 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Garden | Lawn and plants | Fair | Lawn overgrown — not mowed | Medium | Tenant to maintain garden | Yes | 0 | Tenant Action
13 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Garden | Irrigation system | Good | None | None | N/A | N/A | 0 | Clear
14 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Garage | Garage door motor | Good | None | None | N/A | N/A | 0 | Clear
15 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Exterior | External paint | Fair | Fading on north wall | Low | Note for annual repaint | N/A | 0 | Noted
16 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Exterior | Gate and lock | Good | None | None | N/A | N/A | 0 | Clear
17 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Utility Room | Water heater | Good | None | None | N/A | N/A | 0 | Clear
18 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Utility Room | Electrical panel | Good | None | None | N/A | N/A | 0 | Clear
19 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Roof Terrace | Waterproofing | Good | None | None | N/A | N/A | 0 | Clear
20 | Villa 5, GYC | 2026-01-05 | Quarterly | Eng. Raj Kumar | Overall | General cleanliness | Good | Property well maintained | None | Continue quarterly checks | N/A | 0 | Clear

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit