## Launch Plan
Product Launch Marketing Plan
End-to-end launch activity plan with channel budgets and auto duration ¦ ExcelGurukulOnline.com
Activity | Channel | Owner | Start Date | End Date | Duration (Days) | Budget (₹) | Status
Market research and personas | Research | A Patel | 2026-01-05 | 2026-01-23 | 19 | 120000 | In Progress
Positioning and messaging | Strategy | S Iyer | 2026-01-26 | 2026-02-06 | 12 | 80000 | In Progress
Landing page build | Digital | K Nair | 2026-02-09 | 2026-02-27 | 19 | 150000 | In Progress
Teaser social campaign | Social Media | N Desai | 2026-03-02 | 2026-03-20 | 19 | 200000 | In Progress
Influencer partnerships | Influencer | L Bose | 2026-03-09 | 2026-04-10 | 33 | 350000 | In Progress
PR and media kit | PR | R Khan | 2026-03-16 | 2026-03-27 | 12 | 100000 | In Progress
Email nurture sequence | Email | T Menon | 2026-03-23 | 2026-04-17 | 26 | 60000 | In Progress
Paid search campaign | Paid Ads | V Rao | 2026-04-01 | 2026-05-29 | 59 | 400000 | In Progress
Launch event planning | Events | M Gupta | 2026-04-06 | 2026-05-15 | 40 | 450000 | In Progress
Demo video production | Content | P Singh | 2026-04-13 | 2026-05-01 | 19 | 180000 | Planned
App store optimisation | Digital | K Nair | 2026-04-20 | 2026-05-08 | 19 | 50000 | Planned
Launch day webinar | Events | J Reddy | 2026-05-18 | 2026-05-18 | 1 | 90000 | Planned
Retargeting campaign | Paid Ads | V Rao | 2026-05-19 | 2026-06-30 | 43 | 250000 | Planned
Customer referral program | Growth | D Shah | 2026-05-25 | 2026-06-26 | 33 | 120000 | Planned
Post-launch survey | Research | A Patel | 2026-06-08 | 2026-06-19 | 12 | 40000 | Planned
Performance review and ROI | Analytics | G Kumar | 2026-06-29 | 2026-07-10 | 12 | 30000 | Planned
TOTAL | [5 empty] | 2670000

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit