## Bug Defect Log
Bug Defect Log
Track bugs, defects, severity, status and resolution for software projects
Bug ID | Module | Description | Reported By | Date | Severity | Priority | Assigned To | Status | Resolution
BUG-001 | Login | User cannot reset password via email | QA Team | 2026-05-01 | Critical | P1 | Dev A | Open | Under investigation
BUG-002 | Dashboard | Charts not loading on IE browser | QA Team | 2026-05-02 | High | P2 | Dev B | In Progress | Patch in development
BUG-003 | Reports | Export to PDF fails for large datasets | QA Team | 2026-05-03 | Medium | P2 | Dev A | Open | Queued for sprint 3
BUG-004 | Settings | Timezone not saving correctly | Dev B | 2026-05-04 | Low | P3 | Dev C | Closed | Fixed in v2.1.3
BUG-005 | Mobile | UI overlap on iPhone SE screen size | QA Team | 2026-05-05 | Medium | P3 | Dev D | In Progress | CSS fix applied
BUG-006 | API | Rate limit error on bulk import | Dev A | 2026-05-06 | High | P1 | Dev B | Open | API team notified

## 📌 More Info
Excel Gurukul Online — Additional Resources
More Support | Excel Gurukul Online | Action / Link
Need More Excel Templates? | Visit our website for 500+ free & premium templates | https://excelgurukulonline.com/
Browse by Category | 20 categories — Project Management, HR, Finance & more | https://excelgurukulonline.com/templates.php
Project Management Templates | Gantt Charts, Risk Registers, RACI Matrix & more | https://excelgurukulonline.com/templates.php?cat=project-management
HR & Workforce Templates | Attendance, Payroll, Appraisal & more | https://excelgurukulonline.com/templates.php?cat=hr-workforce
Finance & Budget Templates | Budget Planners, EMI Calculator, Debt Tracker & more | https://excelgurukulonline.com/templates.php?cat=personal-finance
Contact / Special Requirements | Need a customised template? We can help! | info@excelgurukulonline.com
💡 TIP: All templates on Excel Gurukul Online are built from real-world business experience. Free samples are available across all 20 categories. Premium versions available at nominal INR pricing.
© 2026 Excel Gurukul Online ¦ excelgurukulonline.com ¦ info@excelgurukulonline.com