## Sprint and Agile Tracker
Sprint and Agile Tracker
Plan and track sprints with user stories, velocity and burndown
Story ID | User Story | Priority | Points | Sprint | Assigned To | Status | % Done | Start | End | Acceptance Criteria
US-001 | As a user I can login with email and password | Critical | 5 | Sprint 1 | Dev A | Done | 100% | 08-Feb-26 | 21-Feb-26 | Login works — session created — error on fail
US-002 | As a user I can reset password via email | High | 3 | Sprint 1 | Dev B | Done | 100% | 08-Feb-26 | 21-Feb-26 | Reset link sent within 60 seconds
US-003 | As admin I can view all user accounts | High | 5 | Sprint 1 | Dev A | Done | 100% | 08-Feb-26 | 21-Feb-26 | Table view with search and filter
US-004 | As user I can view dashboard with KPI tiles | High | 8 | Sprint 2 | Dev B | In Progress | 60% | 22-Feb-26 | 07-Mar-26 | 5 KPI tiles load within 3 seconds
US-005 | As user I can export reports to PDF | Medium | 5 | Sprint 2 | Dev A | In Progress | 40% | 22-Feb-26 | 07-Mar-26 | PDF generated in under 10 seconds
US-006 | As user I can set notification preferences | Medium | 3 | Sprint 3 | Dev B | Backlog | 0% | 08-Mar-26 | 21-Mar-26 | Email and push notifications configurable
US-007 | As admin I can generate audit trail reports | High | 8 | Sprint 3 | Dev A | Backlog | 0% | 08-Mar-26 | 21-Mar-26 | Full activity log with date filters
US-008 | As user I can integrate with third-party CRM | Low | 13 | Sprint 4 | Dev B | Backlog | 0% | 22-Mar-26 | 04-Apr-26 | Salesforce and Zoho CRM sync
SPRINT 1 SUMMARY | Done — 13 pts | Velocity: 13
SPRINT 2 SUMMARY | In Progress — 13 pts | Velocity TBD

## 📌 More Info
Excel Gurukul Online — Technology & IT › IT Project Management
Need More Templates? | Browse 500+ free & premium Excel templates | https://excelgurukulonline.com/
Browse All Categories | 20 categories — find the right template for you | https://excelgurukulonline.com/templates.php
More Technology & IT Templates | See all Technology & IT templates | https://excelgurukulonline.com/templates.php?cat=technology-it
More IT Project Management Templates | See all templates in IT Project Management | https://excelgurukulonline.com/templates.php
Request a Custom Template | Need something specific? Contact us! | info@excelgurukulonline.com
💡 All templates on Excel Gurukul Online are free to download. Premium versions available at nominal INR pricing. Visit https://excelgurukulonline.com to explore all Technology & IT templates.
© 2026 Excel Gurukul Online ¦ https://excelgurukulonline.com ¦ info@excelgurukulonline.com