## IT Change Request Form
IT Change Request Form
Raise and track IT change requests through the change control process
CR ID | Change Title | Requestor | Date | Type | Systems Affected | Business Impact | Risk | Approved By | Approval Date | Impl. Date | Status
CR-2601 | Upgrade DB server v12 to v15 | Dev Lead | 2026-05-01 | Standard | Prod DB | Low — no downtime | Low | IT Manager | 2026-05-03 | 2026-05-10 | Approved
CR-2602 | Add new API endpoint for mobile | Dev A | 2026-05-02 | Standard | API Gateway | Medium | Low | IT Manager | 2026-05-04 | 2026-05-15 | Approved
CR-2603 | Emergency patch — CVE-2026-1234 | CISO | 2026-05-03 | Emergency | All servers | Critical — security | Critical | CTO | 2026-05-03 | 2026-05-03 | Completed
CR-2604 | Migrate file storage to S3 | Infra Lead | 2026-05-04 | Major | File Server | High — 4hr window | Medium | Change Board | 2026-05-10 | 2026-05-25 | Under Review
CR-2605 | Renew SSL certificate — expiry 30-May | IT Admin | 2026-05-05 | Standard | Web servers | High if missed | Medium | IT Manager | 2026-05-06 | 2026-05-28 | Approved
CR-2606 | Deploy bulk email export feature | Dev B | 2026-05-06 | Standard | Email module | Low — new feature | Low | IT Manager | — | 2026-05-20 | Pending

## 📌 More Info
Excel Gurukul Online — Technology & IT › IT Project Management
Need More Templates? | Browse 500+ free & premium Excel templates | https://excelgurukulonline.com/
Browse All Categories | 20 categories — find the right template for you | https://excelgurukulonline.com/templates.php
More Technology & IT Templates | See all Technology & IT templates | https://excelgurukulonline.com/templates.php?cat=technology-it
More IT Project Management Templates | See all templates in IT Project Management | https://excelgurukulonline.com/templates.php
Request a Custom Template | Need something specific? Contact us! | info@excelgurukulonline.com
💡 All templates on Excel Gurukul Online are free to download. Premium versions available at nominal INR pricing. Visit https://excelgurukulonline.com to explore all Technology & IT templates.
© 2026 Excel Gurukul Online ¦ https://excelgurukulonline.com ¦ info@excelgurukulonline.com