## UAT Test Cases Log
UAT Test Cases Log
User Acceptance Testing template with test scenarios and results
Test ID | Module | Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail | Tester | Date | Defect ID
TC-001 | Login | Valid user login | 1.Open app 2.Enter email 3.Enter password 4.Click Login | Email: test@co.in Pass: Test@123 | Dashboard loads — user logged in | Dashboard loaded correctly | Pass | QA Lead | 01-May-26 | —
TC-002 | Login | Invalid password | 1.Enter valid email 2.Enter wrong password 3.Login | Email: test@co.in Pass: Wrong123 | Error: Invalid credentials | Error displayed correctly | Pass | QA Lead | 01-May-26 | —
TC-003 | Login | Account lockout after 5 attempts | 1.Enter wrong password 5 times | Any email | Account locked — message shown | Locked on 5th attempt | Pass | QA Lead | 01-May-26 | —
TC-004 | Dashboard | KPI tiles load correctly | 1.Login 2.Go to dashboard 3.Verify 5 tiles | Valid user account | 5 tiles show data within 3 secs | 4 tiles loaded — Revenue tile blank | Fail | QA Lead | 02-May-26 | BUG-012
TC-005 | Dashboard | Export to PDF | 1.Open dashboard 2.Click Export 3.Select PDF | Valid user | PDF generated in under 10 seconds | PDF generated in 8 secs — correct | Pass | Client | 02-May-26 | —
TC-006 | Reports | Date range filter | 1.Open reports 2.Set date range 3.Apply | Any user account | Report shows only selected date range | Filter worked correctly | Pass | QA Lead | 02-May-26 | —
TC-007 | Admin | Add new user | 1.Login as admin 2.Go to Users 3.Add user | New user details | New user created — email sent | User created — email not sent | Fail | QA Lead | 03-May-26 | BUG-013
TC-008 | Password | Reset via email | 1.Forgot Password 2.Enter email 3.Check inbox | Registered email | Reset link arrives in 60 seconds | Link in 45 secs — new password worked | Pass | QA Lead | 03-May-26 | —

## 📌 More Info
Excel Gurukul Online — Technology & IT › IT Project Management
Need More Templates? | Browse 500+ free & premium Excel templates | https://excelgurukulonline.com/
Browse All Categories | 20 categories — find the right template for you | https://excelgurukulonline.com/templates.php
More Technology & IT Templates | See all Technology & IT templates | https://excelgurukulonline.com/templates.php?cat=technology-it
More IT Project Management Templates | See all templates in IT Project Management | https://excelgurukulonline.com/templates.php
Request a Custom Template | Need something specific? Contact us! | info@excelgurukulonline.com
💡 All templates on Excel Gurukul Online are free to download. Premium versions available at nominal INR pricing. Visit https://excelgurukulonline.com to explore all Technology & IT templates.
© 2026 Excel Gurukul Online ¦ https://excelgurukulonline.com ¦ info@excelgurukulonline.com