## Rollout Plan
Software Rollout Plan
Phased software deployment plan across locations with users, dates and status ¦ ExcelGurukulOnline.com
Phase | Location / Unit | Users | Rollout Date | Trainer | Support Contact | Status
Pilot | Head Office - IT | 25 | 2026-01-12 | Ankit Shah | it.support@company.com | Completed
Pilot | Head Office - Finance | 40 | 2026-01-19 | Ankit Shah | it.support@company.com | Completed
Phase 1 | Mumbai Branch | 85 | 2026-02-02 | Ritu Malhotra | mum.help@company.com | Completed
Phase 1 | Pune Branch | 60 | 2026-02-09 | Ritu Malhotra | pune.help@company.com | Completed
Phase 1 | Nagpur Branch | 35 | 2026-02-16 | Ritu Malhotra | ngp.help@company.com | Completed
Phase 2 | Delhi Branch | 120 | 2026-03-02 | Sameer Khan | del.help@company.com | Completed
Phase 2 | Gurgaon Office | 95 | 2026-03-09 | Sameer Khan | ggn.help@company.com | Completed
Phase 2 | Jaipur Branch | 45 | 2026-03-16 | Sameer Khan | jai.help@company.com | In Progress
Phase 3 | Bengaluru Office | 150 | 2026-04-06 | Divya Menon | blr.help@company.com | In Progress
Phase 3 | Chennai Branch | 110 | 2026-04-13 | Divya Menon | che.help@company.com | Scheduled
Phase 3 | Hyderabad Branch | 90 | 2026-04-20 | Divya Menon | hyd.help@company.com | Scheduled
Phase 4 | Kolkata Branch | 75 | 2026-05-04 | Rahul Bose | kol.help@company.com | Scheduled
Phase 4 | Ahmedabad Branch | 55 | 2026-05-11 | Rahul Bose | amd.help@company.com | Scheduled
Phase 4 | Kochi Branch | 30 | 2026-05-18 | Rahul Bose | koc.help@company.com | Scheduled
Phase 5 | International - Dubai | 40 | 2026-06-01 | Ankit Shah | dxb.help@company.com | Planned
TOTAL

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit