## Release Tracker
SOFTWARE RELEASE TRACKER
Track releases across environments with start and go-live dates and computed duration.
Release | Version | Environment | Start Date | Go-Live Date | Duration (days) | Status
Core Platform | v3.0 | Production | 2026-03-01 | 2026-03-15 | 14 | Released
Payments Module | v2.4 | Production | 2026-03-16 | 2026-03-28 | 12 | Released
Mobile App | v5.1 | Staging | 2026-04-01 | 2026-04-12 | 11 | In Test
Reporting Suite | v1.8 | UAT | 2026-04-05 | 2026-04-20 | 15 | In Test
API Gateway | v4.2 | Production | 2026-04-10 | 2026-04-22 | 12 | Released
Search Service | v2.0 | Staging | 2026-04-15 | 2026-04-30 | 15 | In Test
Notification Engine | v1.3 | Dev | 2026-04-20 | 2026-05-06 | 16 | Building
Admin Console | v3.5 | UAT | 2026-04-25 | 2026-05-09 | 14 | In Test
Data Pipeline | v2.9 | Production | 2026-05-01 | 2026-05-16 | 15 | Released
Auth Service | v6.0 | Staging | 2026-05-05 | 2026-05-19 | 14 | In Test
Billing Engine | v3.1 | Dev | 2026-05-10 | 2026-05-28 | 18 | Building
Customer Portal | v4.0 | UAT | 2026-05-15 | 2026-05-30 | 15 | In Test
Analytics Module | v2.2 | Production | 2026-05-20 | 2026-06-03 | 14 | Released
File Storage | v1.6 | Staging | 2026-05-25 | 2026-06-08 | 14 | In Test
Chat Service | v1.1 | Dev | 2026-06-01 | 2026-06-20 | 19 | Building
Backup Service | v2.7 | Production | 2026-06-05 | 2026-06-18 | 13 | Released

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit