## Sprint Velocity
Sprint Velocity and Burndown Tracker
technology-it ¦ Track planned versus completed story points each sprint with velocity and carry-over
| Sprint | Sprint Dates | Planned Story Points | Completed Story Points | Velocity % | Carry-Over Points
| Sprint 1 | 05-Jan to 16-Jan-2026 | 42 | 38 | 90.48% | 4
| Sprint 2 | 19-Jan to 30-Jan-2026 | 45 | 45 | 100% | 0
| Sprint 3 | 02-Feb to 13-Feb-2026 | 40 | 33 | 82.5% | 7
| Sprint 4 | 16-Feb to 27-Feb-2026 | 44 | 41 | 93.18% | 3
| Sprint 5 | 02-Mar to 13-Mar-2026 | 48 | 44 | 91.67% | 4
| Sprint 6 | 16-Mar to 27-Mar-2026 | 42 | 42 | 100% | 0
| Sprint 7 | 30-Mar to 10-Apr-2026 | 46 | 39 | 84.78% | 7
| Sprint 8 | 13-Apr to 24-Apr-2026 | 40 | 37 | 92.5% | 3
| Sprint 9 | 27-Apr to 08-May-2026 | 50 | 46 | 92% | 4
| Sprint 10 | 11-May to 22-May-2026 | 44 | 44 | 100% | 0
| Sprint 11 | 25-May to 05-Jun-2026 | 42 | 36 | 85.71% | 6
| Sprint 12 | 08-Jun to 19-Jun-2026 | 46 | 42 | 91.3% | 4
| Sprint 13 | 22-Jun to 03-Jul-2026 | 48 | 48 | 100% | 0
| Sprint 14 | 06-Jul to 17-Jul-2026 | 44 | 40 | 90.91% | 4
| Sprint 15 | 20-Jul to 31-Jul-2026 | 42 | 38 | 90.48% | 4
| Sprint 16 | 03-Aug to 14-Aug-2026 | 46 | 43 | 93.48% | 3

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit