## Client Onboarding
Client Onboarding Checklist
Manage freelance client onboarding step by step — consultation, contract, payment, kickoff, and project setup tasks
S.No. | Client Name | Project Type | Onboarding Date | Task / Step | Description | Responsible | Due Date | Completed Date | Status | Notes
1 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Initial Consultation Call | Understand client needs, scope, timeline, and budget | Freelancer | 2026-01-05 | 2026-01-05 | Done | 1-hour discovery call completed
2 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Send Welcome Email | Send welcome email with project overview and next steps | Freelancer | 2026-01-05 | 2026-01-05 | Done | Template used — personalised
3 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Share Questionnaire | Send client questionnaire to capture data sources and requirements | Freelancer | 2026-01-06 | 2026-01-07 | Done | Returned same day
4 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Proposal & Quote | Prepare and send detailed project proposal with pricing and timeline | Freelancer | 2026-01-07 | 2026-01-08 | Done | AED 8,000 approved
5 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Contract Signing | Send, review, and get signed service agreement | Both | 2026-01-08 | 2026-01-09 | Done | DocuSign used
6 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Invoice & Advance Payment | Raise invoice for 50% advance and confirm receipt | Freelancer | 2026-01-09 | 2026-01-10 | Done | AED 4,000 advance received
7 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Access & Data Collection | Receive sample data files and understand data structure | Client | 2026-01-10 | 2026-01-11 | Done | 5 Excel files received
8 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Project Kickoff Meeting | Confirm scope, timeline, milestones, and communication channels | Both | 2026-01-11 | 2026-01-11 | Done | Weekly update agreed
9 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Create Shared Folder / Drive | Set up shared workspace for files, drafts, and feedback | Freelancer | 2026-01-11 | 2026-01-11 | Done | Google Drive shared
10 | Gulf Industries LLC | Excel Dashboard Build | 2026-01-05 | Define KPIs & Dashboard Layout | Agree on KPI metrics, charts, and visual layout before building | Both | 2026-01-12 | 2026-01-13 | Done | Wireframe approved
11 | TechArabia Co. | Monthly Data Reports | 2026-01-08 | Initial Consultation Call | Understand monthly reporting needs and data sources | Freelancer | 2026-01-08 | 2026-01-08 | Done
12 | TechArabia Co. | Monthly Data Reports | 2026-01-08 | Send Welcome Email | Welcome email and project overview sent | Freelancer | 2026-01-08 | 2026-01-08 | Done
13 | TechArabia Co. | Monthly Data Reports | 2026-01-08 | Proposal & Quote | Monthly retainer proposal — AED 3,500 per month | Freelancer | 2026-01-09 | 2026-01-10 | Done | 3-month retainer signed
14 | TechArabia Co. | Monthly Data Reports | 2026-01-08 | Contract Signing | Monthly retainer agreement signed | Both | 2026-01-10 | 2026-01-11 | Done
15 | TechArabia Co. | Monthly Data Reports | 2026-01-08 | Access & Data Collection | Receive monthly data export format and source files | Client | 2026-01-12 | 2026-01-13 | Done | CSV exports agreed
16 | Bright Future Academy | Student Tracker Build | 2026-01-12 | Initial Consultation Call | Understand student data tracking requirements | Freelancer | 2026-01-12 | 2026-01-12 | Done
17 | Bright Future Academy | Student Tracker Build | 2026-01-12 | Share Questionnaire | Capture student data fields, reports needed, user count | Freelancer | 2026-01-13 |  | In Progress | Client yet to return
18 | Bright Future Academy | Student Tracker Build | 2026-01-12 | Proposal & Quote | Prepare proposal once questionnaire received | Freelancer | 2026-01-15 |  | Pending | Awaiting questionnaire
19 | Skyline Properties | Property Portfolio Tracker | 2026-01-15 | Initial Consultation Call | Understand property tracking and ROI reporting needs | Freelancer | 2026-01-15 | 2026-01-15 | Done | 6 properties to track
20 | Skyline Properties | Property Portfolio Tracker | 2026-01-15 | Proposal & Quote | Prepare property tracker proposal with custom fields | Freelancer | 2026-01-16 | 2026-01-17 | Done | AED 6,000 proposal sent — pending approval

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit