## Startup Checklist
Startup Launch Checklist
Step-by-step startup checklist — ideation, legal setup, financial, technology, marketing, and official launch tasks
S.No. | Phase | Task | Description | Responsible | Target Date | Done Date | Status | Cost (AED) | Notes
1 | Ideation | Define business concept | Document the business idea, problem and solution | Founder | 2026-01-01 | 2026-01-02 | Done | 0 | 1-page concept document
2 | Ideation | Market research | Validate demand, target audience, and competitors | Founder | 2026-01-05 | 2026-01-08 | Done | 0 | 50 survey responses collected
3 | Ideation | Business model design | Define revenue streams, pricing, and cost structure | Founder | 2026-01-08 | 2026-01-10 | Done | 0 | Business Model Canvas completed
4 | Legal Setup | Choose business structure | Decide LLC, Freezone, or sole trader | Legal Counsel | 2026-01-10 | 2026-01-12 | Done | 2000 | Dubai Mainland LLC selected
5 | Legal Setup | Trade name registration | Register business name with DED | Legal Counsel | 2026-01-12 | 2026-01-15 | Done | 1500 | ExcelGurukul Online LLC approved
6 | Legal Setup | Trade license application | Apply for trade license — DED | Legal Counsel | 2026-01-15 | 2026-01-22 | Done | 15000 | License received 22 Jan
7 | Legal Setup | MOA drafting and signing | Prepare and notarise Memorandum of Association | Legal Counsel | 2026-01-20 | 2026-01-25 | Done | 3000 | Notarised at Dubai Courts
8 | Legal Setup | Open corporate bank account | Open business current account — Emirates NBD | Founder | 2026-01-25 | 2026-01-29 | Done | 0 | Account active — AED 5K min balance
9 | Financial | Initial capital injection | Transfer seed capital into business account | Founder | 2026-01-29 | 2026-01-29 | Done | 50000 | AED 50K seed capital
10 | Financial | Set up accounting system | Subscribe to accounting software — QuickBooks | Founder | 2026-02-01 | 2026-02-03 | Done | 1200 | Annual subscription
11 | Financial | VAT registration | Register for VAT if turnover exceeds AED 375K | Accountant | 2026-02-01 |  | In Progress | 500 | Threshold not yet reached — monitor
12 | Technology | Domain and hosting setup | Purchase domain and set up web hosting | IT/Founder | 2026-02-01 | 2026-02-02 | Done | 1500 | excelgurukulonline.com live
13 | Technology | Website development | Build WordPress site with template library | Developer | 2026-02-01 | 2026-02-28 | Done | 8000 | Launch version live
14 | Technology | Payment gateway integration | Integrate payment system for premium templates | Developer | 2026-03-01 |  | In Progress | 0 | Payhip vs Razorpay — decision pending
15 | Marketing | Brand identity design | Logo, colour scheme, typography guidelines | Designer | 2026-02-01 | 2026-02-10 | Done | 2500 | Red and white brand confirmed
16 | Marketing | Social media profiles setup | Create LinkedIn, Instagram, YouTube accounts | Marketing | 2026-02-10 | 2026-02-12 | Done | 0 | All handles secured
17 | Marketing | SEO strategy and content plan | Keyword research and content calendar | Marketing | 2026-03-01 | 2026-03-10 | Done | 0 | 100% SEO coverage target
18 | Operations | Admin systems and tools | Set up email, project management, file storage | Founder | 2026-02-01 | 2026-02-05 | Done | 500 | MS365, SharePoint, Teams
19 | Launch | Soft launch — beta version | Release site to select users for feedback | Founder | 2026-03-01 | 2026-03-05 | Done | 0 | 50 beta users — positive feedback
20 | Launch | Official public launch | Full launch with marketing push — all channels | Founder | 2026-03-15 |  | In Progress | 5000 | Launch campaign in progress

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit