## Risk Matrix
Risk Assessment Matrix
Identify and rate risks by likelihood and impact with owner, mitigation and status.
S.No. | Risk ID | Risk Description | Category | Likelihood | Impact | Risk Level | Owner | Mitigation Action | Status
1 | R-01 | Key supplier delay | Operational | Medium | High | High | Procurement | Add backup supplier | Open
2 | R-02 | Data breach | IT Security | Low | High | Medium | IT | Strengthen access control | In Progress
3 | R-03 | Cash flow shortfall | Financial | Medium | High | High | Finance | Maintain reserve fund | Open
4 | R-04 | Staff turnover | HR | Medium | Medium | Medium | HR | Retention programme | In Progress
5 | R-05 | Regulatory change | Compliance | Low | Medium | Low | Legal | Monitor updates | Open
6 | R-06 | Equipment failure | Operational | Medium | Medium | Medium | Operations | Preventive maintenance | In Progress
7 | R-07 | Project overrun | Project | High | Medium | High | PMO | Tighten scope control | Open
8 | R-08 | Currency fluctuation | Financial | Medium | Medium | Medium | Finance | Hedge exposure | Open
9 | R-09 | Reputation damage | Strategic | Low | High | Medium | Marketing | Crisis comms plan | Open
10 | R-10 | Cyber attack | IT Security | Medium | High | High | IT | Deploy monitoring | In Progress
11 | R-11 | Power outage | Operational | Low | Medium | Low | Facilities | Backup generator | Closed
12 | R-12 | Contract dispute | Legal | Low | High | Medium | Legal | Clear terms review | Open
13 | R-13 | Market downturn | Strategic | Medium | High | High | Executive | Diversify revenue | Open
14 | R-14 | Quality defect | Operational | Medium | Medium | Medium | Quality | Tighten QC checks | In Progress
15 | R-15 | Vendor lock-in | IT | Low | Medium | Low | IT | Plan exit strategy | Open
16 | R-16 | Skills shortage | HR | Medium | Medium | Medium | HR | Upskilling plan | In Progress
17 | R-17 | Health and safety | Operational | Low | High | Medium | HSE | Safety training | Closed
18 | R-18 | Late receivables | Financial | High | Medium | High | Finance | Stricter credit terms | Open

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit