## Material Take-Off Template
Material Take-Off Template
ExcelGurukulOnline.com ¦ Construction & Engineering · Project Costing
Item No. | Material Description | Spec / Grade | Unit | Required Qty | Wastage % | Order Qty | Unit Rate (₹) | Total Cost (₹) | Supplier | Lead Time (Days) | Status
── STRUCTURAL MATERIALS ──
S-01 | Cement OPC 53 Grade | 53 Grade | Bags | 850 | 5 | 892.5 | 420 | 374850 | ACC/UltraTech | 3 | To Order
S-02 | TMT Steel Bars 12mm | Fe500D | MT | 12 | 5 | 12.6 | 62000 | 781200 | SAIL | 7 | To Order
S-03 | TMT Steel Bars 8mm | Fe500D | MT | 4 | 5 | 4.2 | 63000 | 264600 | SAIL | 7 | To Order
S-04 | River Sand | Zone II | Cum | 80 | 10 | 88 | 1800 | 158400 | Local Quarry | 2 | To Order
S-05 | Blue Metal 20mm | Crushed | Cum | 60 | 8 | 64.8 | 1600 | 103680 | Local Quarry | 2 | To Order
S-06 | Bricks (First Class) | 230x115x75 | Nos | 25000 | 5 | 26250 | 8 | 210000 | Brick Kiln | 4 | To Order
── FINISHING MATERIALS ──
F-01 | Vitrified Tiles 600x600 | Premium | Sqm | 360 | 10 | 396 | 480 | 190080 | Asian Granito | 5 | To Order
F-02 | Bathroom Wall Tiles | Ceramic 30x45 | Sqm | 125 | 10 | 137.5 | 380 | 52250 | Kajaria | 5 | To Order
F-03 | Interior Paint | Tractor Emulsion | Ltr | 400 | 10 | 440 | 165 | 72600 | Asian Paints | 3 | To Order
F-04 | Exterior Paint | Weather Coat | Ltr | 250 | 10 | 275 | 195 | 53625 | Asian Paints | 3 | To Order
── PLUMBING MATERIALS ──
P-01 | CPVC Pipes 1 inch | ISI Mark | Rmt | 220 | 8 | 237.6 | 185 | 43956 | Astral Pipes | 3 | To Order
P-02 | PVC SWR Pipes 110mm | ISI Mark | Rmt | 165 | 8 | 178.2 | 165 | 29403 | Finolex | 3 | To Order
P-03 | CPVC Fittings | Matching | Lot | 1 | 15 | 1.1 | 35000 | 38500 | Astral Pipes | 3 | To Order
── ELECTRICAL MATERIALS ──
E-01 | FR Wire 2.5 sqmm | 3 core | Mtr | 800 | 8 | 864 | 68 | 58752 | Polycab | 4 | To Order
E-02 | Conduit Pipes 20mm | PVC | Mtr | 500 | 5 | 525 | 22 | 11550 | Precision | 3 | To Order
E-03 | MCB + DB Box | 6A/16/32A | Set | 12 | 2 | 12.2 | 1850 | 22570 | Schneider | 5 | To Order
TOTAL | [7 empty] | 2466016

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit