## Construction Budget
Construction Budget Tracker
Track all construction work packages — budgeted costs, payments, advance amounts, completion percentage, and status
S.No. | Work Package | Category | Contractor / Vendor | Budgeted Cost (AED) | Advance Paid (AED) | Invoiced Amount (AED) | Amount Paid (AED) | Balance Due (AED) | Start Date | End Date | % Complete | Status | Remarks
1 | Site Clearance & Levelling | Civil | Al Baraka Contractors | 45000 | 20000 | 45000 | 45000 | 0 | 2026-01-01 | 2026-01-15 | 100% | Completed
2 | Foundation & Excavation | Civil | Al Baraka Contractors | 180000 | 80000 | 180000 | 160000 | 20000 | 2026-01-10 | 2026-02-05 | 100% | Completed | Final payment due
3 | Concrete Structure — Ground Floor | Structural | Gulf Build LLC | 350000 | 150000 | 350000 | 300000 | 50000 | 2026-02-01 | 2026-02-28 | 100% | Completed
4 | Concrete Structure — First Floor | Structural | Gulf Build LLC | 320000 | 100000 | 280000 | 250000 | 30000 | 2026-03-01 | 2026-03-31 | 85% | In Progress | On schedule
5 | Concrete Structure — Second Floor | Structural | Gulf Build LLC | 300000 | 50000 | 0 | 0 | 300000 | 2026-04-01 | 2026-04-30 | 0% | Not Started
6 | Brick Masonry & Block Work | Civil | NK Civil Works | 120000 | 50000 | 100000 | 90000 | 30000 | 2026-02-15 | 2026-03-31 | 80% | In Progress
7 | Roofing & Waterproofing | Waterproofing | WaterPro UAE | 85000 | 30000 | 0 | 0 | 85000 | 2026-05-01 | 2026-05-31 | 0% | Not Started
8 | Electrical Works | MEP | PowerTech MEP | 150000 | 60000 | 90000 | 80000 | 70000 | 2026-02-01 | 2026-04-30 | 60% | In Progress | First fix complete
9 | Plumbing & Sanitary | MEP | AquaFlow MEP | 130000 | 50000 | 80000 | 70000 | 60000 | 2026-02-01 | 2026-04-30 | 55% | In Progress
10 | HVAC & Air Conditioning | MEP | Cool Air Systems | 200000 | 80000 | 0 | 0 | 200000 | 2026-05-01 | 2026-06-30 | 0% | Not Started | Awarded, not started
11 | Aluminium Doors & Windows | Finishing | AlumPro UAE | 180000 | 70000 | 180000 | 150000 | 30000 | 2026-03-01 | 2026-04-15 | 90% | In Progress | Final fix pending
12 | Internal Plastering | Civil | NK Civil Works | 75000 | 30000 | 50000 | 45000 | 30000 | 2026-03-15 | 2026-04-15 | 65% | In Progress
13 | External Cladding & Paint | Finishing | ColourMax UAE | 90000 | 0 | 0 | 0 | 90000 | 2026-05-01 | 2026-06-30 | 0% | Not Started
14 | Floor Tiling — Ground Floor | Finishing | Tile Masters LLC | 85000 | 35000 | 85000 | 75000 | 10000 | 2026-03-01 | 2026-03-31 | 100% | Completed
15 | Floor Tiling — First Floor | Finishing | Tile Masters LLC | 80000 | 20000 | 40000 | 35000 | 45000 | 2026-04-01 | 2026-04-30 | 50% | In Progress
16 | Bathroom Fittings & Fixtures | Finishing | Royal Sanitary UAE | 95000 | 40000 | 95000 | 80000 | 15000 | 2026-03-15 | 2026-04-30 | 85% | In Progress
17 | Kitchen Cabinetry & Fittings | Finishing | Kitchen World UAE | 120000 | 50000 | 0 | 0 | 120000 | 2026-05-01 | 2026-05-31 | 0% | Not Started
18 | Landscaping & External Works | Civil | Green Thumb LLC | 65000 | 0 | 0 | 0 | 65000 | 2026-06-01 | 2026-06-30 | 0% | Not Started
19 | Security & CCTV System | IT/Security | SafeGuard Tech | 45000 | 20000 | 45000 | 40000 | 5000 | 2026-03-01 | 2026-03-31 | 100% | Completed
20 | Project Management & Supervision | Management | Self / PMC | 80000 | 0 | 40000 | 40000 | 40000 | 2026-01-01 | 2026-06-30 | 50% | In Progress | Monthly billing

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit