## Material Take-Off
Material Take-Off Sheet
Quantify all construction materials — specifications, quantities, wastage, order quantities, rates, costs, suppliers, and delivery status
S.No. | Material Description | Specification | Area / Element | Quantity | Unit | Wastage % | Order Quantity | Unit Rate (AED) | Total Cost (AED) | Supplier | Lead Time (Days) | Order Date | Delivery Date | Status | Notes
1 | Portland Cement OPC 43 | OPC 43 — 50kg bags | All concrete works | 1,200 | Bags | 5% | 1,260 | 28 | 35280 | Gulf Cement LLC | 3 | 2026-01-05 | 2026-01-08 | Ordered | Delivered on time
2 | River Sand — washed | Zone 2 — fine aggregate | Masonry and plaster | 180 | MT | 5% | 189 | 85 | 16065 | Sand Masters UAE | 5 | 2026-01-05 | 2026-01-10 | Ordered
3 | Crushed Aggregate 20mm | Coarse aggregate 20mm | Concrete works | 250 | MT | 5% | 263 | 75 | 19725 | Aggregate Plus UAE | 5 | 2026-01-05 | 2026-01-10 | Ordered
4 | TMT Steel Bars 12mm | Fe500 grade — 12m length | Column and slab rebar | 50 | MT | 5% | 52.5 | 3,800 | 199500 | Steel Arabia Co. | 7 | 2026-01-02 | 2026-01-09 | Delivered | Grade certified
5 | TMT Steel Bars 16mm | Fe500 grade — 12m length | Beam rebar | 35 | MT | 5% | 36.8 | 3,850 | 141580 | Steel Arabia Co. | 7 | 2026-01-02 | 2026-01-09 | Delivered
6 | Concrete Blocks 200mm | Hollow block 400x200x200 | Internal partitions | 8,500 | Nos | 3% | 8,755 | 4.50 | 39398 | Block World UAE | 4 | 2026-01-08 | 2026-01-12 | Ordered
7 | AAC Blocks 200mm | Autoclaved aerated — 600x200 | External walls | 4,200 | Nos | 3% | 4,326 | 8.50 | 36771 | AAC Blocks UAE | 6 | 2026-01-08 | 2026-01-14 | Ordered | Lighter — faster lay
8 | Ceramic Floor Tiles 60x60 | Matt finish — light grey | Floor — all areas | 2,800 | Sqft | 10% | 3,080 | 22 | 67760 | Tile Gallery LLC | 14 | 2026-01-05 | 2026-01-19 | In Transit | ETA 19 Jan
9 | Wall Tiles 30x60 | Glossy white — bathrooms | All bathrooms | 1,200 | Sqft | 10% | 1,320 | 18 | 23760 | Tile Gallery LLC | 14 | 2026-01-05 | 2026-01-19 | In Transit
10 | Gypsum Board 12.5mm | Standard 1200x2400x12.5 | False ceiling | 450 | Sheets | 5% | 473 | 35 | 16555 | Saint-Gobain UAE | 5 | 2026-01-10 | 2026-01-15 | Delivered
11 | PVC Conduit 25mm | Rigid conduit with fittings | All electrical | 2,500 | Mtr | 10% | 2,750 | 3.50 | 9625 | Electro Supplies UAE | 7 | 2026-01-08 | 2026-01-15 | Ordered
12 | Electrical Cable 2.5mm | Twin and earth 2.5mm PVC | Lighting circuit | 5,000 | Mtr | 10% | 5,500 | 4.20 | 23100 | Cable World UAE | 7 | 2026-01-08 | 2026-01-15 | Ordered
13 | Electrical Cable 6mm | Single core 6mm — power | Power circuits | 3,000 | Mtr | 10% | 3,300 | 6.50 | 21450 | Cable World UAE | 7 | 2026-01-08 | 2026-01-15 | Ordered
14 | PVC Pipes 4-inch | Drainage PVC 110mm x 3m | Drainage system | 320 | Nos | 5% | 336 | 42 | 14112 | PVC World Dubai | 5 | 2026-01-10 | 2026-01-15 | Delivered
15 | GI Pipes 2-inch | Galvanised steel — cold water | Cold water supply | 850 | Mtr | 5% | 893 | 28 | 25004 | Pipe Masters UAE | 6 | 2026-01-10 | 2026-01-16 | Ordered
16 | Waterproofing Membrane | SBS modified — 4mm thick | Roof and wet areas | 2,200 | Sqft | 10% | 2,420 | 8.50 | 20570 | WaterPro UAE | 3 | 2026-01-12 | 2026-01-15 | Delivered
17 | Exterior Paint — acrylic | Weather shield — white | External walls | 850 | Litres | 5% | 893 | 18 | 16074 | ColourMax UAE | 4 | 2026-01-15 | 2026-01-19 | Ordered
18 | Interior Emulsion Paint | Matt white — 15L buckets | All internal walls | 1,200 | Litres | 5% | 1,260 | 12 | 15120 | ColourMax UAE | 4 | 2026-01-15 | 2026-01-19 | Ordered
19 | Aluminium Window Frames | Powder coated — dark bronze | All windows | 85 | Nos | 2% | 87 | 850 | 73950 | Aluminium Masters | 21 | 2026-01-02 | 2026-01-23 | In Transit | Custom order — long lead
20 | UPVC Door Frames | White UPVC — 900x2100 | Internal doors | 42 | Nos | 2% | 43 | 380 | 16340 | Door World UAE | 10 | 2026-01-08 | 2026-01-18 | Ordered

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit