## Daily Site Progress Report
Daily Site Progress Report
Daily construction site progress, labour count and activity log
Item | Today's Details | Tomorrow's Plan | Issues/Remarks
Date | 02-May-2026 | 03-May-2026 | —
Site Name | Prestige Lakeside — Block B | — | —
Site Engineer | Mr. Ravi Sharma | — | Present on site
Weather | Sunny — No rain | Sunny forecast | Concreting safe to proceed
LABOUR ATTENDANCE
Masons | 12 | 14 | 2 additional for slab work
Helpers/Labourers | 28 | 30 | Extra needed for RCC
Carpenters | 8 | 8 | For shuttering
Bar Benders | 6 | 8 | TMT work
Total Labour | 54 | 60
WORK COMPLETED TODAY
Slab Shuttering — Level 3 | 75% Complete | Complete 100% | Pending beam bottom
TMT Bar Placement | 60% Complete | Complete 80% | Material delivered
Masonry — Grid C | 100% Complete | Start Grid D | On schedule
MATERIALS
Cement (bags received) | 120 bags | 150 bags | OPC 53 grade
TMT Steel (MT received) | 2.5 MT | 3 MT | Fe500 grade
Aggregate (Cu.m) | 8 Cu.m | 10 Cu.m | 20mm graded
CONCRETE WORK
Concrete Volume Poured | 18 Cu.m | 25 Cu.m (slab) | M25 grade
DAILY PROGRESS STATUS | On Schedule | — | 🟢 All activities on track

## 📌 More Info
Excel Gurukul Online — Construction & Engineering › Site Management
Need More Templates? | Browse 500+ free & premium Excel templates | https://excelgurukulonline.com/
Browse All Categories | 20 categories — find the right template for you | https://excelgurukulonline.com/templates.php
More Construction & Engineering Templates | See all templates in this category | https://excelgurukulonline.com/templates.php?cat=construction‑‑engineering
More Site Management Templates | See all Site Management templates | https://excelgurukulonline.com/templates.php
Request Custom Template | Need something specific? We can help! | info@excelgurukulonline.com
💡 All templates on Excel Gurukul Online are free to download. Premium versions with advanced features available at nominal INR pricing. Visit https://excelgurukulonline.com to explore all Construction & Engineering templates.
© 2026 Excel Gurukul Online ¦ https://excelgurukulonline.com ¦ info@excelgurukulonline.com