## Site Inspection Log
Daily Site Inspection Log
Record daily construction site inspections — findings, risk levels, corrective actions, and closure status
S.No. | Inspection Date | Area / Zone | Inspection Type | Inspector Name | Observation / Finding | Risk Level | Corrective Action Required | Assigned To | Due Date | Status | Remarks
1 | 2026-01-01 | Foundation Zone A | Safety | Eng. Raj Kumar | Minor crack in footing joint | Medium | Re-grout and seal crack | Civil Contractor | 2026-01-03 | Closed
2 | 2026-01-02 | Scaffolding Level 2 | Structural | Eng. Hassan Ali | Loose scaffolding clamp on west side | High | Tighten all scaffolding clamps | Scaffolding Supervisor | 2026-01-04 | Closed
3 | 2026-01-03 | Electrical Room | Electrical | Eng. Priya S. | Exposed wiring near panel DB-3 | High | Insulate exposed wiring immediately | Electrical Contractor | 2026-01-05 | In Progress
4 | 2026-01-04 | Plumbing Area B | Plumbing | Eng. Raj Kumar | Leaking joint at junction pipe | Medium | Replace leaking pipe joint | Plumbing Contractor | 2026-01-06 | Closed
5 | 2026-01-05 | Concrete Pour Zone | Quality | Eng. Hassan Ali | Concrete mix ratio deviation noted | High | Review and correct mix design | Site Engineer | 2026-01-07 | In Progress
6 | 2026-01-06 | Labour Quarters | Safety | Safety Officer | Insufficient ventilation in rooms | Medium | Install ventilation fans | Camp Boss | 2026-01-08 | Closed
7 | 2026-01-07 | Material Storage | Storage | Eng. Raj Kumar | Cement bags stored on wet ground | Low | Elevate storage on pallets | Store Keeper | 2026-01-09 | Closed
8 | 2026-01-08 | Crane Radius Zone | Safety | Safety Officer | Warning tape missing around crane | High | Install warning tape immediately | Crane Operator | 2026-01-10 | Closed
9 | 2026-01-09 | Excavation Pit | Safety | Eng. Hassan Ali | Slope stability needs monitoring | High | Add retaining support | Civil Contractor | 2026-01-11 | In Progress
10 | 2026-01-10 | Roof Structure | Structural | Eng. Priya S. | Bolt missing in purlin connection | Medium | Replace missing bolt | Structural Engineer | 2026-01-12 | Closed
11 | 2026-01-11 | Fire Exit Path | Fire Safety | Safety Officer | Exit sign light not working | High | Replace exit sign light | Electrical Contractor | 2026-01-13 | Closed
12 | 2026-01-12 | Generator Area | Electrical | Eng. Raj Kumar | Fuel leak near generator base | High | Clean fuel spill, check seals | Generator Operator | 2026-01-14 | In Progress
13 | 2026-01-13 | Rebar Tying Zone | Quality | Eng. Hassan Ali | Rebar spacing inconsistent | Medium | Rectify rebar spacing per drawing | Rebar Supervisor | 2026-01-15 | In Progress
14 | 2026-01-14 | Formwork Level 3 | Structural | Eng. Priya S. | Formwork alignment off by 15mm | Medium | Re-align formwork | Formwork Supervisor | 2026-01-16 | Closed
15 | 2026-01-15 | Entrance Gate | Security | Security Mgr | Visitor log not maintained | Low | Implement visitor log system | Security Guard | 2026-01-17 | Pending
16 | 2026-01-16 | Waterproofing Zone | Waterproofing | Eng. Raj Kumar | Blistering in waterproof layer | Medium | Strip and redo waterproofing | Waterproofing Contractor | 2026-01-18 | In Progress
17 | 2026-01-17 | Finishing Floor 2 | Quality | Eng. Priya S. | Tile grout lines uneven | Low | Re-do grout in affected area | Tile Contractor | 2026-01-19 | Pending
18 | 2026-01-18 | Safety Signage Area | Safety | Safety Officer | Missing hardhat sign at entry | Medium | Install required signage | Safety Officer | 2026-01-20 | Closed
19 | 2026-01-19 | Welding Station | Safety | Safety Officer | Welding sparks near flammables | High | Install fire-resistant screen | Welding Supervisor | 2026-01-21 | Closed
20 | 2026-01-20 | Waste Disposal Area | Environmental | Env. Officer | Waste segregation not followed | Medium | Brief workers on segregation rules | Site Supervisor | 2026-01-22 | In Progress

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit