## Delivery Log
Material Delivery Log
Record all construction material deliveries — quantities received, condition, storage location, and delivery discrepancies
S.No. | Delivery Date | Material Name | Category | Supplier | PO Number | Qty Ordered | Qty Delivered | Unit | Delivery Note No. | Received By | Condition | Location Stored | Remarks
1 | 2026-01-02 | Portland Cement OPC 43 | Cement | Gulf Cement LLC | PO-2026-001 | 200 | 200 | Bags | DN-001 | Eng. Raj Kumar | Good | Store A | Full delivery — no issues
2 | 2026-01-03 | TMT Steel Bars 12mm | Steel | Steel Arabia Co. | PO-2026-002 | 10 | 10 | MT | DN-002 | Eng. Hassan Ali | Good | Yard B
3 | 2026-01-04 | River Sand | Aggregates | Al Noor Aggregates | PO-2026-003 | 80 | 75 | m3 | DN-003 | Eng. Raj Kumar | Good | Yard A | 5m3 short — balance due
4 | 2026-01-05 | Coarse Aggregate 20mm | Aggregates | Al Noor Aggregates | PO-2026-003 | 60 | 60 | m3 | DN-004 | Eng. Hassan Ali | Good | Yard A
5 | 2026-01-06 | Red Clay Bricks | Masonry | Brick Masters LLC | PO-2026-005 | 15000 | 14000 | Nos | DN-005 | Eng. Raj Kumar | Good | Store B | 1000 short — delivery 2 pending
6 | 2026-01-07 | Waterproofing Compound | Chemical | Chem Solutions UAE | PO-2026-006 | 200 | 200 | Ltr | DN-006 | Eng. Hassan Ali | Good | Store C
7 | 2026-01-08 | PVC Pipes 4 inch | Plumbing | PVC World Dubai | PO-2026-004 | 300 | 300 | Mtr | DN-007 | Eng. Priya S. | Good | Store D
8 | 2026-01-09 | White Cement | Cement | Gulf Cement LLC | PO-2026-010 | 100 | 100 | Bags | DN-008 | Eng. Raj Kumar | Good | Store A
9 | 2026-01-10 | Plywood 18mm | Wood | Wood & More LLC | PO-2026-015 | 80 | 80 | Sheet | DN-009 | Eng. Hassan Ali | Good | Store B
10 | 2026-01-11 | CPVC Pipes 1 inch | Plumbing | CPVC Solutions | PO-2026-012 | 200 | 200 | Mtr | DN-010 | Eng. Priya S. | Good | Store D
11 | 2026-01-12 | Electrical Conduit Pipe | Electrical | Electro Pipes LLC | PO-2026-011 | 500 | 400 | Mtr | DN-011 | Eng. Raj Kumar | Good | Store E | 100m balance outstanding
12 | 2026-01-13 | Structural Steel I-Beam | Steel | Steel Arabia Co. | PO-2026-013 | 5 | 5 | MT | DN-012 | Eng. Hassan Ali | Good | Yard B
13 | 2026-01-14 | Binding Wire | Steel | Steel Arabia Co. | PO-2026-020 | 100 | 100 | Kg | DN-013 | Eng. Priya S. | Good | Store B
14 | 2026-01-15 | Aluminium Shuttering | Formwork | Form Work UAE | PO-2026-019 | 1000 | 1000 | Sft | DN-014 | Eng. Raj Kumar | Good | Yard C
15 | 2026-01-16 | Bitumen Waterproofing | Chemical | Bitumen Gulf LLC | PO-2026-018 | 300 | 300 | Kg | DN-015 | Eng. Hassan Ali | Good | Store C
16 | 2026-01-17 | Door Frames Teak | Wood | Teak Craft LLC | PO-2026-016 | 20 | 15 | Nos | DN-016 | Eng. Priya S. | Good | Store B | 5 frames short — ETA 25 Jan
17 | 2026-01-18 | GI Wire Mesh | Steel | Steel Net Co. | PO-2026-008 | 50 | 50 | Roll | DN-017 | Eng. Raj Kumar | Good | Yard B
18 | 2026-01-19 | Portland Cement OPC 43 | Cement | Gulf Cement LLC | PO-2026-021 | 300 | 300 | Bags | DN-018 | Eng. Hassan Ali | Good | Store A | 2nd delivery — stock replenishment
19 | 2026-01-20 | Ceramic Floor Tiles | Finishing | Tile Gallery LLC | PO-2026-009 | 400 | 350 | Box | DN-019 | Eng. Priya S. | Good | Store F | 50 boxes short — damaged in transit
20 | 2026-01-21 | Paint Primer | Finishing | ColourMax UAE | PO-2026-016 | 150 | 0 | Ltr |  | N/A | N/A | N/A | Not yet delivered — follow up

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit