## Labour Productivity
Site Labour Productivity Log
Track daily construction site labour productivity — planned vs actual output, hours worked, delay reasons, and productivity rates
S.No. | Date | Trade | Team | Workers Present | Planned Workers | Work Item | Unit | Planned Output | Actual Output | Productivity % | Hours | Output/Hr | Delay Reason | Supervisor
1 | 2026-01-02 | Concrete | Gang A | 8 | 8 | Concrete slab pour — Level 1 | m3 | 40 | 38 | 95% | 8 | 4.75 | None | Eng. Raj Kumar
2 | 2026-01-02 | Steel | Gang B | 6 | 6 | Rebar tying — Column Zone A | Nos | 20 | 22 | 110% | 8 | 2.75 | None | Eng. Hassan Ali
3 | 2026-01-02 | Masonry | Gang C | 10 | 10 | Brick laying — Ground Floor | m2 | 80 | 72 | 90% | 8 | 9.0 | Material delay 1 hr | Eng. Priya S.
4 | 2026-01-03 | Concrete | Gang A | 8 | 8 | Column concrete pour Zone B | m3 | 25 | 25 | 100% | 8 | 3.13 | None | Eng. Raj Kumar
5 | 2026-01-03 | Electrical | Gang D | 5 | 6 | Conduit installation Floor 1 | Mtr | 120 | 95 | 79% | 8 | 11.9 | 1 worker absent | Eng. Hassan Ali
6 | 2026-01-03 | Plumbing | Gang E | 4 | 4 | PVC pipe installation Block A | Mtr | 80 | 85 | 106% | 8 | 10.6 | None | Eng. Priya S.
7 | 2026-01-04 | Steel | Gang B | 6 | 6 | Structural steel erection | Ton | 2 | 1.8 | 90% | 8 | 0.23 | Crane wait 30 min | Eng. Raj Kumar
8 | 2026-01-04 | Concrete | Gang A | 8 | 8 | Beam concrete pour | m3 | 30 | 32 | 107% | 8 | 4.0 | None | Eng. Hassan Ali
9 | 2026-01-05 | Masonry | Gang C | 9 | 10 | Block work First Floor | m2 | 70 | 60 | 86% | 8 | 7.5 | 1 sick, sand delay | Eng. Priya S.
10 | 2026-01-05 | Tiling | Gang F | 5 | 5 | Marble floor tiling Lobby | m2 | 40 | 42 | 105% | 8 | 5.25 | None | Eng. Raj Kumar
11 | 2026-01-06 | Painting | Gang G | 6 | 6 | Primer application Block B | m2 | 300 | 280 | 93% | 8 | 35.0 | Paint supply 1 hr | Eng. Hassan Ali
12 | 2026-01-06 | Electrical | Gang D | 6 | 6 | DB panel installation Floor 2 | Nos | 3 | 3 | 100% | 8 | 0.38 | None | Eng. Priya S.
13 | 2026-01-07 | Concrete | Gang A | 8 | 8 | Roof slab concrete pour | m3 | 35 | 33 | 94% | 8 | 4.13 | Minor formwork fix | Eng. Raj Kumar
14 | 2026-01-07 | Steel | Gang B | 6 | 6 | Rebar fixing Roof Level | Ton | 1.5 | 1.6 | 107% | 8 | 0.20 | None | Eng. Hassan Ali
15 | 2026-01-08 | Plumbing | Gang E | 4 | 4 | Sanitary fitting Block A | Nos | 12 | 10 | 83% | 8 | 1.25 | Fittings not delivered | Eng. Priya S.
16 | 2026-01-08 | Tiling | Gang F | 5 | 5 | Bathroom wall tiling Block A | m2 | 35 | 38 | 109% | 8 | 4.75 | None | Eng. Raj Kumar
17 | 2026-01-09 | Masonry | Gang C | 10 | 10 | Internal partition walls | m2 | 90 | 88 | 98% | 8 | 11.0 | None | Eng. Hassan Ali
18 | 2026-01-09 | Painting | Gang G | 6 | 6 | Final paint coat Block A | m2 | 250 | 265 | 106% | 8 | 33.1 | None | Eng. Priya S.
19 | 2026-01-10 | Concrete | Gang A | 8 | 8 | Staircase concrete pour | m3 | 15 | 15 | 100% | 8 | 1.88 | None | Eng. Raj Kumar
20 | 2026-01-10 | Electrical | Gang D | 5 | 6 | Cable pulling main risers | Mtr | 200 | 160 | 80% | 8 | 20.0 | Cable delivery late | Eng. Hassan Ali

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit