## Group Tasks
GROUP PROJECT TASK TRACKER
Assign and track student group project tasks with owners, deadlines and progress ¦ ExcelGurukulOnline.com
S.No. | Task | Assigned To | Start Date | Due Date | Priority | Status
1 | Define topic & scope | Ananya | 2026-01-06 | 2026-01-09 | High | Done
2 | Background research | Karthik | 2026-01-09 | 2026-01-16 | High | Done
3 | Collect survey data | Meera | 2026-01-12 | 2026-01-22 | High | Done
4 | Literature review | Sahil | 2026-01-16 | 2026-01-26 | Medium | In Progress
5 | Draft introduction | Ananya | 2026-01-20 | 2026-01-27 | Medium | In Progress
6 | Analyse data | Karthik | 2026-01-23 | 2026-02-02 | High | In Progress
7 | Create charts | Meera | 2026-01-27 | 2026-02-04 | Medium | Not Started
8 | Write methodology | Sahil | 2026-01-30 | 2026-02-06 | Medium | Not Started
9 | Write findings | Ananya | 2026-02-03 | 2026-02-10 | High | Not Started
10 | Build presentation | Karthik | 2026-02-06 | 2026-02-13 | High | Not Started
11 | Design poster | Meera | 2026-02-09 | 2026-02-15 | Low | Not Started
12 | Write conclusion | Sahil | 2026-02-11 | 2026-02-16 | Medium | Not Started
13 | Compile references | Ananya | 2026-02-13 | 2026-02-17 | Low | Not Started
14 | Proofread report | Karthik | 2026-02-16 | 2026-02-19 | High | Not Started
15 | Rehearse presentation | Meera | 2026-02-18 | 2026-02-21 | Medium | Not Started
16 | Submit draft | Sahil | 2026-02-20 | 2026-02-22 | High | Not Started
17 | Final corrections | Ananya | 2026-02-22 | 2026-02-24 | High | Not Started
18 | Final submission | Karthik | 2026-02-24 | 2026-02-25 | High | Not Started

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit