## Conference Checklist
Conference Planning Checklist
End-to-end conference planning checklist — from venue booking to post-event follow-up, with costs and status tracking
S.No. | Phase | Task / Action | Description | Responsible | Target Date | Completed Date | Status | Cost (AED) | Notes
1 | Planning | Define conference objectives | Set goals, audience, format, and expected outcomes | Event Manager | 2026-01-01 | 2026-01-02 | Done | 0 | B2B networking + knowledge sharing
2 | Planning | Set budget and get approval | Prepare detailed budget and get sign-off from management | Event Manager | 2026-01-03 | 2026-01-05 | Done | 0 | Budget AED 180,000 approved
3 | Planning | Select date and venue | Shortlist and book conference venue — 200 pax capacity | Event Manager | 2026-01-05 | 2026-01-08 | Done | 45000 | Grand Hyatt Dubai — 15 Mar 2026
4 | Planning | Build event website / landing page | Create registration page with agenda, speakers, and RSVP | Marketing | 2026-01-10 | 2026-01-15 | Done | 5000 | Live at events.company.com
5 | Planning | Identify and invite keynote speakers | Shortlist 3 keynote and 5 panel speakers — confirm participation | Event Manager | 2026-01-10 | 2026-01-20 | Done | 0 | 3 keynotes confirmed
6 | Planning | Launch registration campaign | Email, LinkedIn, and paid ads to drive registrations | Marketing | 2026-01-15 | 2026-01-15 | Done | 12000 | Target 200 registrations
7 | Logistics | Confirm AV and tech setup | Book projector, microphones, screens, recording equipment | Event Manager | 2026-01-20 | 2026-01-25 | Done | 15000 | Professional AV company hired
8 | Logistics | Arrange catering | Coffee breaks x2, lunch buffet for 200 pax | Event Manager | 2026-01-20 | 2026-01-28 | Done | 28000 | Royal Feast Catering confirmed
9 | Logistics | Design and print materials | Banners, name badges, programmes, brochures | Marketing | 2026-01-25 | 2026-02-05 | Done | 8000 | Print Express — delivery 10 Feb
10 | Logistics | Arrange transport and parking | Coordinate shuttle buses and parking allocation for guests | Event Manager | 2026-02-01 |  | In Progress | 6000 | 2 shuttle buses from metro station
11 | Logistics | Set up sponsor exhibition area | Allocate booth spaces, design layout for 8 sponsors | Event Manager | 2026-02-01 |  | In Progress | 0 | Floor plan shared with sponsors
12 | Logistics | Hire event staff and volunteers | Recruit 10 registration staff, 5 ushers, 2 photographers | HR | 2026-02-05 |  | Pending | 12000 | Brief on 10 Mar
13 | Content | Finalise agenda and run of show | Create minute-by-minute schedule for all sessions and breaks | Event Manager | 2026-02-10 |  | In Progress | 0 | Draft v2 in review
14 | Content | Collect speaker presentations | Request and compile all speaker slides by 7 Mar deadline | Event Manager | 2026-03-07 |  | Pending | 0 | Template sent to all speakers
15 | Content | Prepare moderator Q&A guide | Draft questions for each panel session for moderators | Event Manager | 2026-03-07 |  | Pending | 0
16 | On-Day | Set up venue — Day before | Oversee full venue setup including AV, registration, signage | Event Manager | 2026-03-14 |  | Pending | 0 | Access from 14:00 on 14 Mar
17 | On-Day | Registration desk management | Manage attendee check-in, badges, and welcome packs | Event Staff | 2026-03-15 |  | Pending | 0 | Doors open 08:00
18 | On-Day | Speaker and VIP hospitality | Dedicated green room, briefing, and escort for all speakers | Event Manager | 2026-03-15 |  | Pending | 0
19 | Post-Event | Send thank you emails to attendees | Personalised thank you with session recordings and resources | Marketing | 2026-03-18 |  | Pending | 0 | Within 48 hrs of event
20 | Post-Event | Gather feedback and post-event report | Send feedback survey, compile data, and prepare wrap-up report | Event Manager | 2026-03-22 |  | Pending | 0 | Report to management by 25 Mar

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit